Date: March 8, 2010

Derrell Turner

Division Administrator

Federal Highway Administration

380 Jackson Street, Suite 500

St. Paul, MN, 55101

RE:	S.P. 2505-48 (TH 52)

Elk Run Interchange Design-Build Project

Dear Mr. Turner:

Mn/DOT has elected to cancel the current solicitation for bids on the Elk Run Interchange Design-Build Project (in accordance with Section 4.4 of the Request for Qualifications) and begin a new solicitation for bids.

On November 18, 2009, we issued a Request for Qualifications (RFQ) and received Statements of Qualifications (SOQ”s) from six (6) proposers.  The SOQ’s were evaluated; however we did not shortlist during this process.  The new solicitation for bids will start with re-issuance of the Request for Qualifications, scheduled for release on March 12, 2010.

There are a few of reasons for the cancellation.  Olmsted County has requested Mn/DOT add between $5 and $10 million of additional scope to the project (re-alignment of Olmsted County CSAH 12).  With this added scope, Mn/DOT wants to verify the ability of the contractors to obtain an increased performance bond and payment bond for the project.  Also, based on concerns expressed from proposers, we want to verify each team’s project personnel because the schedule delay may have caused certain personnel to be unavailable for this project.

The new procurement schedule is proposed as follows:

Issue RFQ					March 12, 2010

SOQ due date				April 2, 2010

Evaluation of SOQs				April 2, 2010 to April 15, 2010

Provide FHWA with draft RFP		April 12, 2010

Announce Shortlist				April 16, 2010

Issue RFP					April 29, 2010

Technical Proposals due			July 14, 2010

Price Proposals due				July 28, 2010

Evaluation of Technical Proposals	July 14, 2010 to July 29, 2010

Price Proposals opened			July 30, 2010

Anticipated First Notice to Proceed	August 31, 2010

If you have any questions regarding the project, please contact Terry Ward, Elk Run Design-Build Project Manager at 507-286-7688.

Sincerely,

Khani Sahebjam

Deputy Commissioner/Chief Engineer

cc:	Nelrae Succio, District Engineer – District 6

Greg Paulson, Assistant District Engineer – District 6

Terry Ward, Elk Run Interchange Design-Build Project Manager

Amber Blanchard, Design-Build Program Manager