National Road Research Alliance (NRRA)

Geotechnical Team Meeting

Thursday, March 16, 2017

12:30 pm – 1:30 pm (CST)

Meeting Notes

Action Items

- Team Members - Long Term Research statement needs Updated/Completed by Friday March 24th – Please provide your comments to the whole team so everyone is up to speed on the latest version.

- Terry Beaudry/John Siekmeier will develop the final version due April 6th based on your comments.

- Bob Filipzak will post the latest versions on the website – Make sure he is CCed on any updates.

Topics Discussed at the Meeting

- Welcome & Introductions

- NRRA Update

  - Executive Committee approved 2017 funding

  - Tech Transfer Process Approved

  - NRRA Workshop & Conference – May 23-24, 2017

  - Construction Letting – April 27, 2017 (change)

- Long Term Research Work Plans

  - Final Reviews / ok process

  - Two studies into one document on the team web site

- Short Term/Technology Transfer

  - Online Problem Statements

    - Sub-team updates

    - Tasks required

  - Contracting Status

- NRRA Contract Timing Discussion (1st draft)

| April 1 | Long Term Research - Drafts by technical teams |  |  |  |
| --- | --- | --- | --- | --- |
| April 15 | Long Term Research - Sent to MnDOT Master List (Universities) |  |  |  |
| April 15 | Long Term Testing or Short Term Tech Transfer (Under 100K sent to Trap List Member - Direct Select) |  |  |  |
| May 1 | Long Term Testing or Short Term Tech Transfer (Proposals back from Trap List Member) |  |  |  |
| June 1 | Long Term Research - Proposals Due from Universities |  |  |  |
| June 1 | Long Term Testing or Short Term Tech Transfer (Contracted Early Date) |  |  |  |
| June 15 | Long Term Research - Reviewed and selected by technical teams (presentations?) |  |  |  |
| July 1 | Long Term Research - Executive Committee Reviews technical teams selections for approval |  |  |  |
| August 15 | Long Term Research - Contracts Awarded early date |  |  |  |

- Contracting (covered last meeting 3/2/2017)

- TRAP CERTIFIED LIST PROGRAM (Direct Select) $100,000 max

  - 4-6 Weeks Process Time

  - List of contractors – http://www.dot.state.mn.us/consult/documents/certified-lists/trap.pdf

- MnDOT Contracting Discussion / Options

  - MASTER CONTRACT PROGRAM (Direct Select)

    - 4-6 Weeks Process Time

      - List of Universities (12/1/2016 List from Shannon)

        - Iowa State University

        - Michigan Technological University

        - Montana State University (Western Transportation Institute)

        - North Dakota State University

        - The Texas A&M University System (Texas Transportation Institute)

        - University of Minnesota & University of Minnesota Duluth

        - University of New Hampshire

        - University of Pittsburgh

        - University of Wisconsin-Madison

        - Minnesota State University – Mankato

        - St. Cloud State University

  - FORMAL REQUEST FOR PROPOSAL (Non-Direct Select)

    - (RFP) Contracts over $100,001

    - 3-4 Month Process Time

- Summarize/Prioritize Action Items