## weblist
Score | Route | Description | High-Level Cost Estimate for Planning Purposes | Year Planned (FY) | Comments
85 | MN4 | Reclaim and overlay from Highway 19 (Fairfax) to Highway 12 (Hector) | 9200000 | 2026
85 | MN68 | Reclaim and overlay from Canby to Minneota | 13000000 | 2031
83 | MN24 | Medium overlay Highway 12 (Litchfield) to Highway 15 | 8800000 | Not Selected | This section has not been selected because it is a thin whitetopping test section (4-inch bonded concrete overlay in 2015). District will continue to monitor performance for research purposes.
81 | MN30 | Thin mill and overlay from Minnesota / South Dakota State Line to 8th Ave (Pipestone) | 1200000 | 2029
81 | US75 | Cold in place recycling and medium overlay from Yellow Medicine County Road 3 (Canby) to 0.4 mi. S. of US 212 | 4000000 | Not selected | Project was not selected due to fiscal constraints in 2030 (no new non-NHS projects were added in FY 2030)
81 | US75 | Medium overlay from Murray County Road 3 to Hwy212 | 4000000 | Not Selected | Not a district priority. Will continue to monitor pavement performance.
80 | MN271 | Reclaim and overlay from Highway 19 to Minnesota/South Dakota State Line | 4900000 | 2022
80 | US75 | Medium overlay from Pipestone Creek to Lake Benton | 5400000 | 2028
78 | MN30 | Reclaim and overaly from US 59 to Murray/Cottonwood Co. Line | 4900000 | 2026
78 | MN40 | Medium mill and overlay from Highway 59 (Milan) to Highway 29 | 4000000 | 2026
78 | MN22 | Medium overlay from Hutchinson to Highway 7 | 3300000 | Not Selected | Candidate for reconstruction in 2034
75 | US59 | Reclaim and overlay from 15th Ave. (Clarkfield) to US 212 | 3800000 | Not selected
75 | MN22 | Thin overlay from US 12 to Fredericks Ave. (Eden Valley) | 1100000 | 2027
75 | MN19 | Reclaim and overlay from Ivanhoe to Lincoln County Road 5 | 13900000 | 2030
75 | US59 | Reclaim and overlay from 15th Ave to west junction of Hwy212 | 3800000 | Not Selected
74 | MN68 | Reclaim and overlay from US 71 to 0.2 mi. W. of MN 67 (Morgan) | 3900000 | Not selected
74 | MN68 | Reclaim and overlay from Hwy71 to Hwy 57 in Morgan | 3900000 | Not Selected
74 | MN40 | Reclaim and overlay Old Highway 277 to Kandiyohi County Road 5 (Willmar) | 12700000 | 2029
74 | MN55 | Medium overlay from Stearns/Meeker County Line to Eden Valley | 3000000 | Not Selected | Candidate for preventive maintenance in 2024
73 | MN30 | Cold in place recycling and medium overlay from US 75 to Ravine St. (Lake Wilson) | 4300000 | Not selected
73 | MN30 | Medium overlay from Hwy75 to Ravine St in Lake Wilson | 4300000 | Not Selected
71 | MN67 | Thin mill and overlay from MN 23 to Upper Sioux Agency State Park | 1000000 | 2028 | Project was selected because a thin mill & overlay is a low cost treatment with a large performance benefit for this segment (as indicated by low levels of cracking)
71 | MN119 | Medium mill and overlay from Highway 212 (Dawson) to Highway 40 | 2700000 | Not Selected | Candidate for preventive maintenance in 2021
69 | MN4 | Reclaim and overlay from Hector to Cosmos | 10100000 | Not Selected | Candidate for preventive maintenance in 2021
67 | MN68 | Thin mill and overlay from from CR 6 (Wabasso) to US 71 | 1100000 | 2029 | Project was selected because a thin mill & overlay is a low cost treatment with a large performance benefit for this segment (as indicated by low levels of cracking)
67 | MN68 | Thin mill and overlay from Redwood County Road 6 in Wabasso to south junction with Hwy71 | 1100000 | 2029 | Project was selected because a thin mill & overlay is a low cost treatment with a large performance benefit for this segment (as indicated by low levels of cracking)
65 | MN40 | Medium mill from Highway 119 to Highway 59 (Milan) | 3600000 | 2025 | Coordinated with other projects
65 | MN68 | Reclaim and overlay from Redwood County Road 3 (Morgan) to Redwood/Brown County Line | 3100000 | Not Selected | Candidate for reconstruction in 2030
65 | MN7 | Reclaim and overlay Highway 71 to Highway 4 (Cosmos) | 13000000 | Not Selected
65 | MN7 | Reclaim and overlay from Highway 4 (Cosmos) to Highway 22 | 7400000 | Not Selected | Candidate for preventive maintenance in 2025
64 | MN4 | Reclaim and overlay from Cosmos to Meeker County Road 23 | 5400000 | 2022 | This section has been prioritized due to maintenance patching losing effectiveness because of the level of deterioration.
64 | MN267 | Reclaim and overlay from Iona to Highway 30 | 4000000 | Not Selected
63 | MN68 | Reclaim and overlay from South Dakota/Minnesota State Line to Canby | 6400000 | Not Selected
62 | MN29 | Reclaim and overlay from Airport Ave (Montevideo) to MN 40 | 3700000 | Not selected
62 | MN29 | Medium mill and overlay from west junction of Highway 40 to east junction Highway 40 and additional locations on Highway 40 | 5200000 | 2024 | Coordinated with projects on Highway 40
62 | MN67 | Reclaim and overlay from Redwood Falls to Fergus Ave. (Morgan) | 8600000 | Not Selected
62 | MN29 | Reclaim and overlay from Airport Trail to Hwy 40 | 3700000 | Not Selected
61 | MN274 | Reclaim and overlay from Wood Lake to Highway 23 | 6500000 | Not Selected
59 | MN67 | Reclaim and overlay from Travers Ln. to Highway 19 | 12300000 | Not Selected
58 | MN67 | Reclaim and overlay from US 75 toUS 59 (Clarkfield) | 7200000 | Not selected
58 | MN68 | Reclaim and overlay Highway 71 to Redwood County Road 3 (Morgan) | 7700000 | Not Selected
58 | MN67 | Reclaim and overlay from Hwy 75 to Hwy59 near Clarkfield | 7200000 | Not Selected
54 | US59 | Reclaim and overlay from Yellow Medicine County Road 3 to Clarkfield | 4100000 | Not Selected
42 | MN22 | Thin overlay from 0.1 mi. E. of MN 7 to 0.2 mi. W. of MN 7 | 100000 | Not selected
42 | MN22 | Thin overlay from .1 miles east of Hwy 7 to .2 miles west of Hwy 7 | 100000 | Not Selected
40 | MN67 | Thin mill and overlay Highway 23 (Granite Falls) to Travers Ln. | 2100000 | Not Selected
39 | MN269 | Thin overlay from South Dakota/Minnesota State Line to Highway 23 (Jasper) | 600000 | Not Selected
37 | MN9 | Thin overlay from Kandiyohi County Road 7 (Sunberg) to Kandiyohi / Swift Co. Line | 100000 | Not selected
37 | MN9 | Thin overlay from Kandiyohi County Road 7 to Kandiyohi/Swift County line | 100000 | Not Selected
36 | US75 | Thin overlay from 4th St. N. (Pipestone) to Pipestone County Road 22 | 100000 | Not Selected
32 | MN29 | Thin overlay from MN 40 to Chippewa / Swift Co. Line | 400000 | Not selected
32 | MN29 | Thin overlay from Hwy 40 to Chippewa/Swift County Line | 400000 | Not Selected
31 | MN68 | Thin overlay on from Highway 19 to Redwood County Road 32 (Milroy) | 700000 | Not Selected
29 | MN19 | Thin overlay from Reference point 3 to Reference point 4 | 200000 | Not selected
29 | MN19 | Thin overlay from Reference pt 003 to Reference pt 004 | 200000 | Not Selected
6 | MN22 | Thin overlay from Sibley / McLeod Co. Line to US 212 | 200000 | Not selected
6 | MN330 | Thin overlay from Highway 14 to University of Minnesota SW Research and Outreach Center | 500000 | Not Selected
6 | MN22 | Thin overlay from Sibley/McLeod County line to Hwy212 | 200000 | Not Selected
3 | MN104 | Thin mill and overlay Highway 9 to Kandiyohi/Pope County Line | 1400000 | Not Selected