## Non-NHS
Total Score | Route | Description | High-Level Cost Estimate for Planning Purposes | Year Planned (FY) | Comments
87 | MN67 | Construct cul-de-sac on Hwy 67 at entrance to Upper Sioux Agency State Park and remove pavement between cul-de-sac and bridge #87011. | 620000 | Not Selected
85 | MN68 | Resurface Hwy 68 from Porter to Minneota; upgrade sidewalks to meet ADA standards in Porter, Taunton and Minneota; replace box culverts and bridges along project area. | 10500000 | 2032
85 | MN68 | Resurface Hwy 68 from Canby to Minneota; upgrade sidewalks to meet ADA standards in Porter, Taunton and Minneota; replace box culverts and bridges along project area. | 10900000 | 2033
85 | MN4 | Resurface Hwy 4 from Fairfax to Hector. | 14200000 | 2026/2027
83 | MN24 | Medium overlay Highway 12 (Litchfield) to Highway 15 | 8800000 | Not Selected | This section has not been selected because it is a thin whitetopping test section (4-inch bonded concrete overlay in 2015). District will continue to monitor performance for research purposes.
81 | MN30 | Resurface Hwy 30 from the Minnesota/South Dakota state line to 8th St in Pipestone. | 1600000 | 2029
81 | US75 | Cold in place recycling and medium overlay from Yellow Medicine County Road 3 (Canby) to 0.4 mi. S. of US 212 | 4000000 | Not selected | Project was not selected due to fiscal constraints in 2030 (no new non-NHS projects were added in FY 2030)
81 | US75 | Medium overlay from Murray County Road 3 to US212 | 4000000 | Not Selected | Not a district priority will continue to monitor pavement performance.
80 | US75 | Resurface Hwy 75 from Pipestone Creek to S Valley St in Lake Benton. | 9300000 | 2030/2031
78 | MN30 | Resurface Hwy 30 from Hwy 59 to the Murray/Cottonwood county line; replace bridge over Des Moines River. | 14400000 | 2028/2029
78 | MN22 | Medium overlay from Hutchinson to Highway 7 | 3300000 | Not Selected | Candidate for reconstruction in 2034
75 | MN22 | Resurface Hwy 22 from Hwy 12 to Eden Valley. | 9300000 | 2032
75 | MN19 | Resurface Hwy 19 from Ivanhoe to CR 5. | 22700000 | 2031/2032
75 | US59 | Reclaim and overlay from 15th Ave. (Clarkfield) to W. JCT. US 212 | 3800000 | Not selected
74 | MN40 | Reclaim and overlay Old Highway 277 to Kandiyohi County Road 5 (Willmar) | 12700000 | 2026
74 | MN40 | Resurface Hwy 40 from CR 4 to Willmar. | 18500000 | 2030/2031
74 | MN68 | Reclaim and overlay from N. JCT. US 71 to 0.2 mi. W. of MN 67 (Morgan) | 3900000 | Not selected
74 | MN68 | Reclaim and overlay from US71 to Hwy 57 in Morgan | 3900000 | Not Selected
74 | MN55 | Medium overlay from Stearns/Meeker County Line to Eden Valley | 3000000 | Not Selected | Candidate for preventive maintenance in 2024
73 | MN22 | Resurface Hwy 22 from Hwy 212 to Cedar Ave in Glencoe; update sidewalks in Glencoe to meet ADA standards. | 3000000 | 2023
73 | MN30 | Cold in place recycling and medium overlay from US 75 to Ravine St. (Lake Wilson) | 4300000 | Not selected
71 | MN67 | Resurface Hwy 67 from Hwy 23 to the Upper Sioux Agency State Park. | 3300000 | 2029
71 | US75 | Resurface Hwy 75 from CR 9 to Hwy 30 in Pipestone. | 4700000 | Not Selected
71 | MN119 | Medium mill and overlay from Highway 212 (Dawson) to Highway 40 | 2700000 | Not Selected
70 | MN15 | Resurface Hwy 15 from Hwy 12 in Dassel to Meeker/Stearns county line. | 9724000 | 2024/2025
69 | MN4 | Reclaim and overlay from Hector to Cosmos | 10100000 | Not Selected
68 | MN4 | Resurface Hwy 4 from Cosmos to Meeker CR 23. (4701-32) | 3060000 | 2023 | This section has been prioritized due to maintenance patching losing effectiveness because of the level of deterioration.
67 | MN68 | Resurface Hwy 68 from Wabasso to Hwy 71. | 1900000 | 2030
65 | MN40 | Resurface Hwy 40 from Hwy 119 to 5th Street in Milan. | 4900000 | 2025/2026 | Coordinated with other projects
65 | MN7 | Reclaim and overlay Highway 71 to Highway 4 (Cosmos) | 13000000 | Not Selected
65 | MN7 | Reclaim and overlay from Highway 4 (Cosmos) to Highway 22 | 7400000 | Not Selected | Candidate for preventive maintenance in 2025
65 | MN68 | Reclaim and overlay from Redwood County Road 3 (Morgan) to Redwood/Brown County Line | 3100000 | Not Selected | Candidate for reconstruction in 2030
64 | MN267 | Reclaim and overlay from Iona to Highway 30 | 4000000 | Not Selected
63 | MN40/US75 | Resurface Hwy 40 from Hwy 75 to Western Ave; resurface Hwy 75 from Hwy 40 to 8th St in Madison; upgrade sidewalks to meet ADA standards. | 2651000 | 2023
63 | US75 | Reconstruct Hwy 75 from S Valley St in Lake Benton to south jct of Hwy 14. | 5500000 | 2027
63 | MN68 | Reclaim and overlay from South Dakota/Minnesota State Line to Canby | 6400000 | Not Selected
62 | MN29/MN40 | Resurface Hwy 29 from west jct of Hwy 40 to east jct of Hwy 40; resurface Hwy 40 from east jct of Hwy 29 to Chippewa CR 4. | 7400000 | 2029/2033
62 | MN67 | Reclaim and overlay from Redwood Falls to Fergus Ave. (Morgan) | 8600000 | Not Selected
62 | MN29 | Reclaim and overlay from Airport Ave (Montevideo) to MN 40 | 3700000 | Not selected
61 | MN274 | Reclaim and overlay from Wood Lake to Highway 23 | 6500000 | Not Selected
59 | MN67 | Reclaim and overlay from Travers Ln. to Highway 19 | 12300000 | Not Selected
58 | MN68 | Reclaim and overlay Highway 71 to Redwood County Road 3 (Morgan) | 7700000 | Not Selected
58 | MN67 | Reclaim and overlay from US 75 to US59 near Clarkfield | 7200000 | Not Selected
56 | MN68 | Resurface Hwy 68 from N Grant St in Minneota to Hwy 59 in Marshall, excluding the city of Ghent; upgrade sidewalks on Hwy 19 from Hwy 23 to Tiger Dr and on Hwy 59 from Windstart St to Susan Dr in Marshall to meet ADA standards. | 2700000 | 2024
56 | MN68 | Resurface Hwy 68 from N Grant St in Minneota to CR 33 in Marshall, excluding the city of Ghent. | 890910 | 2024
54 | US59 | Reclaim and overlay from Yellow Medicine County Road 3 to Clarkfield | 4100000 | Not Selected
42 | MN22 | Thin overlay from .1 miles east of Hwy 7 to .2 miles west of Hwy 7 | 100000 | Not Selected
40 | MN67 | Thin mill and overlay Highway 23 (Granite Falls) to Travers Ln. | 2100000 | Not Selected
39 | MN269 | Thin overlay from South Dakota/Minnesota State Line to Highway 23 (Jasper) | 600000 | Not Selected
37 | MN9 | Thin overlay from Kandiyohi County Road 7 (Sunberg) to Kandiyohi / Swift Co. Line | 100000 | Not selected
36 | US75 | Thin overlay from 4th St. N. (Pipestone) to Pipestone County Road 22 | 100000 | Not Selected
32 | MN29 | Thin overlay from Hwy 40 to Chippewa/Swift County Line | 400000 | Not Selected
31 | MN68 | Thin overlay on from Highway 19 to Redwood County Road 32 (Milroy) | 700000 | Not Selected
29 | MN19 | Thin overlay from Reference point 3 to Reference point 4 | 200000 | Not selected
6 | MN330 | Thin overlay from Highway 14 to University of Minnesota SW Research and Outreach Center | 500000 | Not Selected
5 | MN22 | Thin overlay from Sibley/McLeod County Line to Highway 212 | 400000 | Not Selected
3 | MN104 | Thin mill and overlay Highway 9 to Kandiyohi/Pope County Line | 1400000 | Not Selected