## Sheet1 (hidden)
Score | Route | NHS? | Description | High Level Cost Estimate for Planning Purposes | Year Planned (FY) | Comments | Color
77 | I35 | NHS | Medium mill and overlay from US 8 to MN95 | 15700000 | Not Selected | Program limited by available funding. Proposed thin overlay within next few years. | R
50 | I35 | NHS | Medium mill and overlay from Scott County road 2 to MN50 | 6400000 | Not Selected | Program limited by available funding. | R
45 | I35 | NHS | Medium mill and overlay from MN95 to Chisago County Road 9 | 6700000 | Not Selected | Program limited by available funding. | R
25 | I35 | NHS | Medium mill and overlay from Chisago County Road 9 to Chisago/Pine County line | 8600000 | Not Selected | Program limited by available funding. | R
25 | I35 | NHS | Medium mill and overlay from I35W/E to US8 | 6400000 | Not Selected | Program limited by available funding. | R
87 | I35 | NHS | Repair road surface, from County Rd 70 to 35E/35W split and from County Road 50 to the 35E/35W split | 37000000 | 2029 | Poor pavement conditions. | Y
64 | I35E | NHS | Replace pavement on I-35E from north exit of Shepard Rd to Hwy 5 (W 7th St) and replace bridge 9534 over Shepard Rd in St Paul | 11416000 | 2026 | Poor pavement conditions. | G
64 | I35E | NHS | Resurface road from Shepard Rd to MN 5 | 2500000 | 2026 | Projected poor pavement conditions. | G
75 | I35E | NHS | Medium mill and overlay from University Ave to Cayuga/Railroad Bridge | 2100000 | Not Selected | Program limited by available funding. Section is predominantly bridge decks. | R
66 | I35E | NHS | Medium mill and overlay from 76th St to 66th ST | 900000 | Not Selected | Program limited by available funding. | R
29 | I35E | NHS | Medium mill and overlay from Cayuga to Little Canada Rd | 7700000 | Not Selected | Program limited by available funding. | R
28 | I35E | NHS | Medium mill and overlay from Ramsey County Road 96 to 80th St | 10600000 | Not Selected | Program limited by available funding. | R
17 | I35E | NHS | Medium mill and overlay from County Road E to County Road 96 | 2300000 | Not Selected | Program limited by available funding. | R
11 | I35E | NHS | Medium mill and overlay from south of I-35W to I35E/W | 1300000 | Not Selected | Program limited by available funding. | R
95 | I35E | NHS | Repair and replace road surface from Lone Oak Rd to 10th St bridge | 18400000 | 2031 | Projected poor pavement conditions. | Y
95 | I35E | NHS | Repair road surface from Little Canada Rd to County Rd E bridge | 8000000 | 2031 | Repair early distresses. | Y
94 | I35E | NHS | Repair road from I-35W/I-35E split to Lone Oak Rd | 109200000 | 2030 | Projected poor pavement conditions. | Y
| I35E | NHS | I-35E From: Exit TH 5 TO: 0.031 mi. N of 10th Street Thin Bituminous Mill and Overlay | 7200000 | 2028 | Projected poor pavement conditions. | Y
50 | I35W | NHS | Resurface road, replace bridge 6583 and ADA improvements from I-35W/I-35E split to 0.08 miles north of Cliff Rd in Burnsville and replace bridge 9779 and 9780 on Hwy 13 | 66802000 | 2025, 2026 | Mobility needs; bridge replacement coordination. | G
49 | I35W | NHS | Improve mobility, reconstruct I-35W/I-494 interchange( construct 7 new bridges), replace 5 bridges and repair 27V45 and 27892 on I-494 eastbound from East Bush Lake Rd to HWY 77, westbound from Hwy 77 to MN100 and northbound I-35W to westbound I-494 in Bloomington, Richfield and Edina | 330900000 | 2023, 2025 | Poor pavement conditions. Coordinate with 494 CoC project. | G
31 | I35W | NHS | Resurface road, auxiliary lane, acceleration lane, drainage and ADA improvements on I-35W from MN River bridge to 0.1 mile south of W 82nd St in Bloomington | 12776000 | 2023 | Poor pavement conditions. Coordinate with 494 CoC project. | G
81 | I35W | NHS | Medium mill and overlay from Washington Ave bridge to 4th St Bridge | 1600000 | Not Selected | This is new pavement but is predominantly comprised of St. Anthony Falls bridge deck. 2020 RQI is excellent. | R
78 | I35W | NHS | Medium mill and overlay from 42nd st bridge to Chicago Ave Bridge | 6500000 | Not Selected | Construction of Lake St project at time of DIV run, bypass pavement is rough. | R
70 | I35W | NHS | Medium mill and overlay from 76th St to 66th ST | 1800000 | Not Selected | Program limited by available funding. | R
59 | I35W | NHS | Medium mill and overlay from County Road C to Sunset Ave | 15100000 | Not Selected | Program limited by available funding. | R
27 | I35W | NHS | Medium mill and overlay from Sunset Ave to I35W/I35E | 7100000 | Not Selected | Program limited by available funding. | R
90 | I35W | NHS | Medium mill and overlay from 4th St bridge to Ramsey County Road C | 8000000 | Not Selected | RQI does not reflect on the ground conditions | R
90 | I35W | NHS | Medium mill and overlay from MN13 to 106th St | 4000000 | Not Selected | Construction of I-35W River Crossing at time of DIV run, bypass pavement is rough. | R
89 | I35W | NHS | Repair road from 66th St to 42nd St bridge | 11000000 | 2031 | Repair early distresses. | Y
38 | I35W | NHS | Repair and resurface road from Portland Ave to Washington Ave | 6000000 | 2031 | Projected poor pavement conditions. | Y
88 | I394 | NHS | Medium mill and overlay from MN100 to Washington Ave N | 3200000 | Not Selected | Recent major rehab. Low RQI attributed largely to high percentage of bridge decks. Also, after a recent lane reconfiguration of WB, part of the outside lane is on rough bituminous shoulder. | R
89 | I394 | NHS | Resurface road from I-494/US 212 to MN 100 | 43000000 | 2029 | Projected poor pavement conditions. | Y
91 | I494 | NHS | Rehab five bridges, rehab pavement and shoulders, replace lighting, reconstruct pedestrian trail and drainage work on I-494 between Pilot Knob Rd in Eagan and 24th Ave in Bloomington | 62000000 | 2023 | Poor pavement conditions. Coordinate with 494 Corridors of Commerce project. | G
29 | I494 | NHS | Rehab pavement and lighting on northbound I-494 exit ramp to Lake Rd in Woodbury | 563209 | 2023 |  | G
81 | I494 | NHS | Medium mill and overlay from Tamarack bridge to Hardman bridge | 6100000 | Not Selected | RQI does not reflect on the ground conditions | R
54 | I494 | NHS | Medium mill and overlay from US12 to I-94 | 12800000 | Not Selected | Program limited by available funding. | R
29 | I494 | NHS | Medium mill and overlay from I-94/694 to Lake Dr | 2300000 | Not Selected | Program limited by available funding. | R
23 | I494 | NHS | Medium mill and overlay from I94/694 to Tamarack Rd | 800000 | Not Selected | Program limited by available funding. | R
90 | I494 | NHS | Medium mill and overlay from 24th Ave to France Ave | 29400000 | Not selected | Poor pavement conditions. Coordinate with 494 Corridors of Commerce project. | R
88 | I494 | NHS | Medium mill and overlay from 5th Ave to Dakota/Hennepin County Line | 13600000 | Not Selected | RQI does not reflect on the ground conditions | R
85 | I494 | NHS | Medium mill and overlay from Hardman bridge to 5th Ave | 2200000 | Not Selected | RQI does not reflect on the ground conditions | R
95 | I494 | NHS | Repair road from France Ave to US 12 | 18000000 | 2030 | Preventive maintenance. | Y
73 | I694 | NHS | Medium mill and overlay from County Road 10 to Anoka Isanti County Line | 1000000 | Not Selected | Under construction at time of DIV run. New concrete pavement at system interchange (94/494/694). | R
55 | I694 | NHS | Medium mill and overlay from Lexington Ave to MN49 | 4600000 | Not Selected | Program limited by available funding. | R
83 | I694 | NHS | Medium mill and overlay from I-494/694 to Lexington Ave | 2900000 | Not Selected | This segment consists of older concrete pavement with recent CPR and fairly new UBOLs. 2020 RQI is very good to excellent. Minor CPR is ongoing due to dowel bar issues. | R
94 | I694 | NHS | Repair road from MN49 to the west end of bridge at US61 | 8000000 | 2031 | Repair early distresses. | Y
94 | I694 | NHS | Repair road from US 61 to CSAH 10 | 15300000 | 2032 | Repair early distresses. | Y
60 | I694 | NHS | Resurface road from E Dupont to I-35W | 40000000 | 2030 | Projected poor pavement conditions. | Y
83 | I94 | NHS | Resurface road, traffic management system, drainage, signing, lighting, guardrail, noise wall, Hudson frontage Rd resurfacing, median barrier and ADA improvements on I-94 from Hwy 120 (Century Ave) in Oakdale to St Croix River in Lakeland and Construct EB auxiliary lane on I-94 from I-94/494/694 in Oakdale to Hwy 19 (Woodbury Dr) in Woodbury and Widen and strengthen bituminous shoulders, update traffic management system, improve drainage, add bituminous cross overs on I-94 from MN 120 in Oakdale to St Croix River in Lakeland | 43697400 | 2023, 2024 | Poor pavement conditions | G
43 | I94 | NHS | Medium mill and overlay from Mounds Blvd to Ramsey/Washington County line | 6800000 | Not Selected | Program limited by available funding. | R
38 | I94 | NHS | Medium mill and overlay from Exit 207 to I494 | 14500000 | Not Selected | Program limited by available funding. | R
33 | I94 | NHS | Medium mill and overlay from Wright/Hennepin County line | 3400000 | Not Selected | Program limited by available funding. | R
90 | I94 | NHS | Medium mill and overlay from I-494 to Nicollet Ave bridge | 27400000 | Not Selected | RQI does not reflect on the ground conditions | R
100 | I94 | NHS | Resurface road from Nicollet Ave to Western Ave | 36000000 | 2031 | Projected poor pavement conditions. | Y
76 | MN100 | NHS | Medium mill and overlay from I-494 to Cedar Lake Bridge | 10900000 | Not Selected | RQI does not reflect on the ground conditions | R
96 | MN100 | NHS | Resurface road from the Cedar Lake Rd to I-694 | 18000000 | 2027 | Poor pavement conditions; preventive maintenance. | Y
46 | MN101 | NHS | Repair and resurface road from I-94 to County Rd 38 | 8800000 | 2026 | Poor pavement conditions. | G
70 | MN101 | NHS | Resurface road from Hwy 5 (W 78th St) to Hwy 10/Townline Rd, resurface road, drainage repairs and ADA improvements on Hwy 101 (W 192nd Ave) from Hwy 5 to Townline Rd in Chanhassen/Eden Prairie | 1799000 | 2024 | Poor pavement conditions. | G
68 | MN101 | NHS | Medium mill and overlay from NB split with US169 to SB merge with US169 | 3400000 | Not Selected | Program limited by available funding. | R
61 | MN101 | NHS | Minor concrete pavement repair, from CR 38 to US 10 | 3500000 | 2027 | Poor pavement conditions. | Y
87 | MN120 | Non-NHS | Reconstruct road from 4th St in Maplewood to Hwy 244 in White Bear Lake | 15559000 | 2027 |  | Y
77 | MN120 | Non-NHS | Resurface road from Ridge Dr to 4th St. | 1200000 | 2031 | Projected poor pavement conditions. | Y
72 | MN121 | NHS | Resurface pavement, signals, drainage and ADA on Hwy 121 (Lyndale Conn) from 0.5 miles west of I-35W pedestrian bridge over Lyndale Ave to W 58th St in Mpls | 1540000 | 2025 |  | G
55 | MN121 | NHS | Medium mill and overlay from I35W to Pedestrian bridge | 300000 | Not Selected | Program limited by available funding. | R
74 | MN13 | NHS | Medium mill and overlay from MN13 to Dakota Ave | 700000 | Not Selected | Program limited by available funding. | R
72 | MN13 | NHS | Medium mill and overlay from Dakota to Washburn ave | 1600000 | Not Selected | Program limited by available funding. | R
66 | MN13 | NHS | Medium mill and overlay from .4 miles west of Dakota Ave to .2 miles east of Dakota ave | 700000 | Not Selected | Program limited by available funding. | R
65 | MN13 | NHS | Medium mill and overlay from Dakota County Line to Washburn Ave | 700000 | Not Selected | Program limited by available funding. | R
40 | MN13 | NHS | Medium mill and overlay from Washburn Ave to I-35 | 1400000 | Not Selected | Program limited by available funding. | R
90 | MN13 | NHS | Medium mill and overlay from I-35W to Yankee Doodle Rd | 6900000 | Not selected | RQI does not match on the ground conditions | R
78 | MN13 | NHS | Medium mill and overlay from Scott County Road 42 to Connelly Pkwy | 700000 | Not selected | RQI does not match on the ground conditions | R
73 | MN13 | NHS | Medium mill and overlay legs to and from Scott County Road 21 roundabout | 300000 | Not selected | Very new pavement either side of new roundabout. | R
71 | MN13 | NHS | Medium mill and overlay from Yankee Doodle Rd to I494 | 900000 | Not selected | RQI does not match on the ground conditions | R
68 | MN13 | NHS | Medium mill and overlay from MN282 to Scott County Road 21 roundabout | 2000000 | Not selected | Program limited by available funding. | R
27 | MN13 | NHS | Medium mill and overlay from Connelly Pkwy to old MN101 | 2000000 | Not selected | Program limited by available funding. | R
27 | MN13 | NHS | Medium mill and overlay from MN13 to MN149 | 200000 | Not selected | Program limited by available funding. | R
70 | MN13 | NHS | Repair concrete from I-494 to MN 55 | 5000000 | 2031 |  | Y
43 | MN13 | NHS | Reconstruct road from Eagle Creek Ave to County Rd 42 | 3500000 | 2030 | Projected poor pavement conditions. | Y
69 | MN149 | Non-NHS | Medium mill and overlay from MN3 to Albano Tr | 200000 | Not selected | Program limited by available funding. | R
64 | MN149 | Non-NHS | Medium mill and overlay from Albano Tr to MN55 | 2600000 | Not selected | Program limited by available funding. | R
58 | MN149 | Non-NHS | Medium mill and overlay from Mendota Heights Rd to MN5/7th St | 2500000 | Not selected | Program limited by available funding. | R
57 | MN149 | Non-NHS | Medium mill and overlay from I-494 to Mendota Heights Rd | 600000 | Not selected | Program limited by available funding. | R
47 | MN19 | NHS | Resurface road from the Leseuer/Scott county line to the Scott/Rice county line - Future Project | 2700000 | 2036 |  | Y
21 | MN20 | Non-NHS | Resurface road from MN 19 to MN 50 | 5000000 | 2032 | Poor pavement conditions. 2020 RSL 2 to 10 years. | Y
77 | MN21 | NHS | Medium mill and overlay from MN19 to Scott County Road 37 | 300000 | Not selected | Program limited by available funding. Short urban section. | R
76 | MN21 | NHS | Medium mill and overlay from Sawmill Rd to Mill St | 300000 | Not selected | RQI does not match on the ground conditions | R
73 | MN21 | NHS | Medium mill and overlay from 7th St to Sawmill Rd | 4300000 | Not selected | RQI does not match on the ground conditions | R
39 | MN21 | NHS | Resurface road from Mill St to US169 | 1500000 | 2031 | Poor pavement conditions. | Y
62 | MN243 | Non-NHS | Medium mill and overlay from MN95 to St Croix River | 700000 | Not selected | Program limited by available funding. | R
20 | MN244 | Non-NHS | Rebuild road from County Rd. 12 to MN 96 | 4000000 | 2031 |  | Y
74 | MN25 | NHS | Medium mill and overlay from MN5 to MN7 | 3900000 | Not Selected | Program limited by available funding. | R
71 | MN25 | NHS | Medium mill and overlay from Scott County line to MN5 | 7100000 | Not selected | RQI does not match on the ground conditions | R
59 | MN25 | NHS | Resurface road from US 212 to MN 5 | 2600000 | 2031 | Projected poor pavement conditions. 2020 RSL 11 years. | Y
33 | MN25 | NHS | Resurface road from US 169 to Minnesota River bridge | 2400000 | 2031 | Poor pavement conditions. | Y
69 | MN252 | NHS | Medium mill and overlay from 85th to MN610 | 1100000 | Not Selected | Program limited by available funding. | R
59 | MN252 | NHS | Medium mill and overlay from I-94 WB in Brooklyn Center to .4 miles north of I-94 | 500000 | Not Selected | Program limited by available funding. | R
68 | MN252 | NHS | Resurface road from I-94 to 85th St | 8500000 | 2031 | Poor pavement conditions. Coordination with 252 CoC project. | Y
72 | MN280 | NHS | Repair pavement, guardrail, rehab 13 bridges on Hwy 280 from junction with I-94 in St Paul to junction with I-35W in Roseville and close median on Hwy 280 at Broadway in Lauderdale and install signals at Kosata Ave and ramps with Energy Park Dr in St Paul | 25763000 | 2026, Future | Poor pavement conditions; coordinate with bridge work. | G
32 | MN280 | NHS | Unbonded overlay from Como to I-35W | 23400000 | 2027 | Poor pavement conditions. | Y
74 | MN284 | NHS | Reconstruct road from US 212 to 122nd St | 11000000 | 2031 |  | Y
78 | MN3 | NHS | Medium mill and overlay from MN50 to Dakota County Road 58 | 3300000 | Not selected | Program limited by available funding. 2020 Remaining service life is predicted 9 to 15 years. | R
73 | MN3 | NHS | Medium mill and overlay from Bridge 19045 to Mendota Rd | 500000 | Not selected | RQI does not match on the ground conditions | R
71 | MN3 | NHS | Medium mill and overlay from MN149 to Bridge 19045 | 1300000 | Not selected | Program limited by available funding. 2020 Remaining service life 0 to 7 years. Short PCC section driving down Remaining service life. | R
77 | MN3 | NHS | Resurface road from Rice County line to MN 50 | 6500000 | 2028 | Poor pavement conditions. | Y
72 | MN3 | NHS | Reconstruct the road from Amana Trail to MN 62 | 8800000 | 2031 |  | Y
69 | MN3 | NHS | Resurface road from 145th St to MN 149 | 4500000 | 2031 |  | Y
69 | MN316 | NHS | Resurface pavement on Hwy 316 (Red Wing Blvd) from south jct Hwy 61 to Tuttle in Hastings and widen shoulder at various locations on Hwy 316 (Red Wing Blvd) in Ravenna Township | 6222000 | 2025 | Poor pavement conditions. | G
66 | MN36 | NHS | Resurface pavement on Hwy 36 from Jct I-35W in Roseville to just east Edgerton in Maplewood/Little Canada and extend auxiliary lane and reconstruct ramp at I-35W SB/Cleveland Ave to Hwy 36 EB | 12352000 | 2025 | Poor pavement conditions; maintenance liability. | G
59 | MN36 | NHS | Medium mill and overlay from Washington Ave to MN95 | 1800000 | Not Selected | Program limited by available funding. | R
75 | MN41 | NHS | Resurface road including pavement marking and guardrail work at Hwy 41 intersection with Peavey Rd in Chaska | 82000 | 2023 |  | G
62 | MN41 | NHS | Resurface Hwy 41 from 0.23 miles north of Pioneer Trl in Chaska to Hwy 5 (Arboretum Blvd) in Chanhassen | 1834000 | 2023 | Poor pavement conditions. | G
67 | MN41 | NHS | Medium mill and overlay from US169 to Pioneer Trail | 1200000 | Not Selected | Program limited by available funding. | R
62 | MN41 | NHS | Medium mill and overlay from MN5 to MN7 | 1100000 | Not selected | Program limited by available funding. | R
31 | MN41 | NHS | Repair road from Count Hwy 61 to Hundertmark Rd | 12980000 | 2032 | Poor pavement conditions. | Y
19 | MN47 | NHS | Resurface road and ADA improvements on Hwy 47 (University Ave) from Cree St to Anoka/Isanti County line in St Francis | 2662000 | 2025 | Safety. Poor pavement conditions. | G
61 | MN47 | NHS | Medium mill and overlay from US 10 to Industry Ave | 700000 | Not selected | Program limited by available funding. | R
30 | MN47 | NHS | Medium mill and overlay from US10 to .4 miles NW of US10 | 300000 | Not selected | Program limited by available funding. | R
72 | MN47 | NHS | Resurface, drainage, sidewalks and ADA work on Hwy 47 from Hwy 65 to just south of 27th northeast Ave in Mpls | 3400000 | 2027 |  | Y
33 | MN47 | NHS | Resurface MN 47 from 142nd Ave to 153rd Ave (Alpine Dr) | 1600000 | 2028 | Projected poor pavement conditions. Project has previously been deferred. 2020 RSL 5 years. | Y
33 | MN47 | NHS | Resurface road from 153rd Ave (Alpine Dr) to Cree St NW/St. Francis | 15000000 | 2029 | Projected poor pavement conditions. | Y
32 | MN47 | NHS | Resurface road from 40th Ave to US 10 | 10500000 | 2030 | Poor pavement conditions. | Y
43 | MN5 | NHS | Medium mill and overlay from I-494 to Hennepin/Ramsey County line | 3900000 | Not Selected | Program limited by available funding. | R
81 | MN5 | NHS | Medium mill and overlay from Hennepin/Ramsey County Line to Munster Ave | 600000 | Not selected | Not selected. Program limited by available funding. Short section of PCC before and after river bridge. Bridge surface is pulling average RQI down. | R
69 | MN5 | NHS | Medium mill and overlay from Birch St to Scandia Rd | 1100000 | Not selected | Program limited by available funding. | R
65 | MN5 | NHS | Medium mill and overlay from .2 miles W of Carver County Road 10 to .2 miles east of Carver County Road 10 | 200000 | Not selected | Program limited by available funding. | R
59 | MN5 | NHS | Medium mill and overlay from MN25 to Carver County Road 10 | 1900000 | Not selected | Program limited by available funding. | R
55 | MN5 | NHS | Medium mill and overlay from Carver County Road 10 to Oak Ave | 200000 | Not selected | Program limited by available funding. | R
67 | MN5 | NHS | Resurface road from St. Clair Ave to bridge over I94 | 14439000 | 2028 | Poor pavement conditions. | Y
60 | MN5 | NHS | Repair road from MN 41 to Eden Prairie Rd | 18300000 | 2032 | Much of this is older PCC with ride impacted by isolated crack slabs, some of which are from subsurface utility issues. | Y
24 | MN5 | NHS | Resurface road from County Rd 11 to MN 41 | 5000000 | 2032 | Projected poor pavement conditions. | Y
76 | MN50 | Non-NHS | Resurface Hwy 50 (240th St) from Hwy 52 (Emery Ave/Rochester Blvd) in Hampton to Hwy 61 in Douglas Township | 6568000 | 2026 | Poor pavement conditions. | G
57 | MN50 | Non-NHS | Medium mill and overlay from MN3 to US52 | 4300000 | Not selected | Program limited by available funding. | R
79 | MN51 | Non-NHS | Resurface, guardrail and ADA on Hwy 51 (Snelling Ave N) from north end of bridge over MN 36 in Roseville to 0.1 mile north of Grey Fox Rd in Arden Hills | 6477000 | 2026 | Poor pavement conditions. ADA, bike/ped, and drainage needs. | G
70 | MN51 | Non-NHS | Resurface road and ADA improvements on Hwy 51 (Snelling Ave) from Grand Ave to St Clair Ave in St Paul | 1760000 | 2024 |  | G
74 | MN51 | Non-NHS | Medium mill and overlay from Grey Fox Rd to I694 | 300000 | Not selected | Recently repaired in 2021 | R
25 | MN51 | Non-NHS | Resurface road from W 7th to Dayton Ave | 6100000 | 2030 | Poor pavement conditions. | Y
82 | MN55 | NHS | Repair pavement and bridge culverts 6732 and 6745 and add turn lane on Hwy 55 (Olson Memorial Hwy) from Old Rockford Rd in Plymouth to just east General Mills Blvd in Golden Valley | 18102000 | 2024 | Poor pavement conditions. | G
65 | MN55 | NHS | Resurface roadway, sidewalk ADA and signal replacement on MN 55 west of BNSF bridge to I-94 | 5800000 | 2026 | Poor pavement conditions. Frontage road and ADA needs. | G
62 | MN55 | NHS | Resurface pavement, construct trail and turn lane reconstruction at Dahlberg Drive on Hwy 55 (Olson Memorial Pkwy) from 0.2 miles west of Hwy 100 in Golden Valley to west end of bridge over BNSF tracks in Mpls | 3337000 | 2025 | Poor pavement conditions. | G
62 | MN55 | NHS | Medium mill and overlay from Pine Bend Trail to Hastings CL | 3500000 | Not Selected | Program limited by available funding. | R
35 | MN55 | NHS | Medium mill and overlay from General Mills Blvd to Schaper Rd | 2100000 | Not Selected | Program limited by available funding. | R
64 | MN55 | NHS | Resurface Road from Highway 52 to US 61 | 19500000 | 2030 | Poor pavement conditions. | Y
63 | MN55 | NHS | Repair road from County Rd 63 to US 52 | 7000000 | 2028 | Poor pavement conditions. | Y
46 | MN55 | NHS | Resurface road from the Wright-Hennepin county line to Fernbrook | 22000000 | 2028 | Poor pavement conditions. | Y
15 | MN56 | NHS | Resurface road from the Goodhue/Dakota County line to MN 50/US 52 | 5180000 | 2031 | Projected poor pavement conditions. 2020 RSL 4 to 11 years. | Y
39 | US12 | Non-NHS | Reconstruction and mill and overlay from Wayzata Blvd to I-494 | 60600000 | 2026 | Concrete segment is in poor condition; maintenance liability | G
36 | US12 | Non-NHS | Resurface road, lighting, drainage improvements, ADA, pier protection on bridges 27129 and 27130 on Hwy 12 (Wayzata Blvd) from 0.5 miles west Shoreline Dr in Orono to 0.5 miles east I-494 in Minnetonka | 20854000 | 2026, Future | Poor pavement conditions. | G
78 | US169 | Non-NHS | Repair pavement on Hwy 169 (Johnson Memorial Hwy) from Hwy 21 (Broadway St N) to 0.54 mile west of CR 15 (Marystown Rd) in Shakopee and modify access on Hwy 169 (Johnson Memorial Hwy) from Hwy 21 (Broadway St N) to Bluff Dr in Shakopee | 10978000 | 2024 | Poor pavement conditions. | G
19 | US212 | Non-NHS | Resurface road, repair 2 bridges and install cable median barrier on Hwy 212 from 0.14 miles west of CR 36 (Lake St) in Cologne to 0.7 miles east of CR 36 (Lake St) in Cologne | 10103000 | 2023 | Poor pavement conditions. | G
44 | US52 | Non-NHS | Resurface road, cable median guardrail and repair 2 bridges on Hwy 52 from 0.2 miles north of CR 86 (280th St/Rochester Blvd) in Hampton Township to 0.2 miles north of CR 42 (145th St) in Rosemount | 65000000 | 2023 | Poor pavement conditions. | G
34 | US61 | Non-NHS | Resurface road from N Jct Hwy 316 to 4th St | 6600000 | 2026 | Poor pavement conditions. | G
40 | US8 | Non-NHS | Resurface, drainage repair, construct pond from jct I-35 in Forest Lake to 0.1 miles west of Wyoming Ave in Chisago City, and construct left turn lane on Hwy 8 (Lake Blvd) at Hazel Ave and close 250th St at MN 8 in Wyoming Township | 14032000 | 2025 | Coordination with County safety improvements. Poor pavement conditions. | G
76 | MN610 | NHS | Medium mill and overlay from MN252 to Mississippi River Bridge | 1000000 | Not Selected | Program limited by available funding. | R
56 | MN610 | NHS | Medium mill and overlay from I-94 to Elm Creek Blvd | 2400000 | Not Selected | Program limited by available funding. | R
29 | MN610 | NHS | Medium mill and overlay from Elm Creek Blvd to US 169 | 2700000 | Not Selected | Program limited by available funding. | R
66 | MN610 | NHS | Repair road from US 169 to Mississippi River | 20000000 | 2031 | Projected poor pavement conditions. | Y
64 | MN610 | NHS | Repair and resurface MN 610 from Mississippi River to Coon Rapids Blvd | 15000000 | 2028 |  | Y
57 | MN62 | NHS | Repair pavement on Hwy 62 between Hwy 13 and 0.2 miles east of I-35E in Mendota Heights | 5172000 | 2024 | Poor pavement conditions. | G
74 | MN62 | NHS | Medium mill and overlay from Tracy ave bridge to Penn Ave Bridge | 3200000 | Not Selected | Program limited by available funding. | R
73 | MN62 | NHS | Medium mill and overlay from 43rd Ave to Mendota Bridge | 1600000 | Not Selected | Program limited by available funding. | R
65 | MN62 | NHS | Medium mill and overlay from I-494 to Clearwater Dr | 300000 | Not Selected | Program limited by available funding. | R
63 | MN62 | NHS | Medium mill and overlay from Portland Ave to 28th ave | 1800000 | Not Selected | Program limited by available funding. | R
62 | MN62 | NHS | Medium mill and overlay from Clearwater to Tracy Ave | 3300000 | Not Selected | Program limited by available funding. | R
61 | MN62 | NHS | Medium mill and overlay from Portland Ave bridge to .154 miles east of Portland bridge | 200000 | Not Selected | Program limited by available funding. | R
55 | MN62 | NHS | Medium mill and overlay from Clearwater Dr to .32 miles east of Clearwater | 400000 | Not Selected | Program limited by available funding. | R
69 | MN62 | NHS | Medium mill and overlay from I-35E to US52 | 3500000 | Not selected | Program limited by available funding. | R
80 | MN62 | NHS | Resurface road from Penn Ave to Portland Ave | 11000000 | 2032 | Repair early distresses. | Y
53 | MN62 | NHS | Resurface road from 28th Ave to MN 55 | 10000000 | 2027 | Poor pavement conditions. | Y
78 | MN65 | NHS | Repair pavement and replace bridges 6817 ( new bridge # 02X06) and 9417 (02X07) over Coon Creek and ADA, signal replacement on Hwy 65 (Central Ave) from CR 10 (Mounds View Blvd) in Spring Lake Park to 217th Ave in East Bethel, cable median barrier from Bunker Lake Blvd to 237th | 39898000 | 2024 | Poor pavement conditions. | G
68 | MN65 | NHS | Medium mill and overlay from 26th St to 10th ST | 1300000 | Not Selected | Program limited by available funding. | R
29 | MN65 | NHS | Medium mill and overlay from south of E Moore Lake Dr to Anoka County Road 10 | 3100000 | Not Selected | Program limited by available funding. | R
78 | MN65 | NHS | Resurface road form 53rd Ave NE to South Moore Lake Dr | 3000000 | 2027 | Poor pavement conditions. | Y
43 | MN65 | NHS | Repair road from 217th Ave to Anoka-Isanti County line | 18000000 | 2029 | Repair early distresses. | Y
70 | MN65 | NHS | Resurface road from 37th Ave NE Ave to 53rd NE | 5200000 | 2032 | Projected poor pavement conditions. | Y
78 | MN7 | Non-NHS | Medium mill and overlay from Shady Oak Rd to Texas Ave | 3000000 | Not Selected | RQI does not reflect on the ground conditions | R
73 | MN7 | Non-NHS | Medium mill and overlay from Texas Ave to Railroad Bridge | 700000 | Not Selected | RQI does not reflect on the ground conditions | R
67 | MN7 | Non-NHS | Medium mill and overlay from Railroad bridge to MN100 | 900000 | Not Selected | Program limited by available funding. | R
66 | MN7 | Non-NHS | Medium mill and overlay from I-494 to Shady Oak Road | 1000000 | Not Selected | Program limited by available funding. | R
81 | MN7 | Non-NHS | Resurface road from the Hennepin/Carver County line to Division St | 23100000 | 2031 | Recent resurfacing project. Construction in progress at time of DIV run. Roughness at intersection contribute to poor ride. | Y
72 | MN7 | Non-NHS | Resurface road from TH 25 to Carver County Line | 6500000 | 2030 | Projected poor pavement conditions. | Y
31 | MN7 | Non-NHS | Repair road from W end of 494 bridge. to I-494 | 500000 | 2030 | Poor pavement conditions. | Y
18 | MN77 | NHS | Resurface Hwy 77 (Cedar) from 138th St (CR 23) in Bloomington to the Dakota-Hennepin County line in Apple Valley | 35838000 | 2026, Future | Poor pavement conditions. | G
60 | MN77 | NHS | Medium mill and overlay from Minnesota River bridge to I-494 | 3100000 | Not Selected | Program limited by available funding. | R
72 | MN95 | NHS | Medium mill and overlay from Point Rd to I-94 | 2800000 | Not selected | RQI does not match on the ground conditions | R
68 | MN95 | Non-NHS | Medium mill and overlay from Mulberry to St Saint Croix Trail | 500000 | Not selected | Program limited by available funding. | R
80 | US52 | Non-NHS | Medium mill and overlay from MN65 to University Ave | 1600000 | Not selected | Program limited by available funding. | R
76 | US10 | Non-NHS | Medium mill and overlay from Foley Blvd to MN56 | 4100000 | Not Selected | RQI does not reflect on the ground conditions | R
71 | US10 | Non-NHS | Medium mill and overlay from east of 114th Ave NW to east Foley Blvd | 2200000 | Not Selected | RQI does not reflect on the ground conditions | R
59 | US10 | Non-NHS | Medium mill and overlay from Fairoak Ave to US169/MN47 | 900000 | Not Selected | Program limited by available funding. | R
29 | US10 | Non-NHS | Medium mill and overlay from MN101 to Cleveland Ave | 3400000 | Not Selected | Program limited by available funding. | R
78 | US10 | Non-NHS | Medium mill and overlay from US61 to .1 miles east of US61 | 100000 | Not selected | Program limited by available funding. Short piece of 4 lane east of USTH 61. Recently received a UTBWC surface treatment. | R
73 | US10 | Non-NHS | Medium mill and overlay from I-35W to I694 | 3000000 | Not selected | RQI does not match on the ground conditions | R
70 | US12 | Non-NHS | Medium mill and overlay from County Road 90 to eastern Independence City limits | 400000 | Not Selected | Program limited by available funding. | R
64 | US12 | Non-NHS | Medium mill and overlay from Hennepin County Road 29 to Wayzata Blvd exit | 3000000 | Not Selected | Program limited by available funding. | R
61 | US12 | Non-NHS | Medium mill and overlay from Railroad bridge to 7th St | 300000 | Not Selected | Program limited by available funding. | R
72 | US169 | Non-NHS | Medium mill and overlay from Anderson Lakes Pkwy to Valley View Rd | 1500000 | Not Selected | Program limited by available funding. | R
72 | US169 | Non-NHS | Medium mill and overlay from Catrerbury rd to Valley View Rd | 8600000 | Not Selected | Program limited by available funding. | R
68 | US169 | Non-NHS | Medium mill and overlay from Elm creek Blvd to Mississippi River Bridge | 500000 | Not Selected | Program limited by available funding. | R
65 | US169 | Non-NHS | Medium mill and overlay from MN282 to MN21 | 1400000 | Not Selected | Program limited by available funding. | R
59 | US169 | Non-NHS | Medium mill and overlay from .1 miles north of Ash St to 1.2 miles north of Ash St | 1300000 | Not Selected | Program limited by available funding. | R
58 | US169 | Non-NHS | Medium mill and overlay from 4.5 miles north of MN19 to 5.7 miles north of MN19 | 1100000 | Not Selected | Program limited by available funding. | R
58 | US169 | Non-NHS | Medium mill and overlay from Elm Creek Blvd to US10 | 1400000 | Not Selected | Program limited by available funding. | R
57 | US169 | Non-NHS | Medium mill and overlay from LeSueur/Scott County line to MN19 | 400000 | Not Selected | Program limited by available funding. | R
36 | US169 | Non-NHS | Medium mill and overlay from Valley View Rd to US 212/MN62 | 1900000 | Not Selected | Program limited by available funding. | R
21 | US169 | Non-NHS | Medium mill and overlay from MN19 to MN25 | 4500000 | Not Selected | Program limited by available funding. | R
18 | US169 | Non-NHS | Medium mill and overlay from 1.2 miles north of MN282 to .27 miles north of MN282 | 5900000 | Not Selected | Program limited by available funding. | R
18 | US169 | Non-NHS | Medium mill and overlay from 93rd Ave to Elm Creek Blvd | 4000000 | Not Selected | Program limited by available funding. | R
15 | US169 | Non-NHS | Medium mill and overlay from MN25 to Ash St | 1800000 | Not Selected | Program limited by available funding. | R
91 | US169 | Non-NHS | Medium mill and overlay from MN55 to 77th Ave | 7800000 | Not Selected | Program limited by available funding. | R
83 | US169 | Non-NHS | Medium mill and overlay from MN 62 to MN55 | 6300000 | Not Selected | Program limited by available funding. | R
69 | US212 | Non-NHS | Medium mill and overlay from MN5 to Tacoma Ave | 3500000 | Not Selected | Program limited by available funding. | R
68 | US212 | Non-NHS | Medium mill and overlay from 2.2 miles east of MN284 to 4 lane section | 2200000 | Not Selected | Program limited by available funding. | R
66 | US212 | Non-NHS | Meduim mill and overlay from MN5 to .4 miles east of MN5 | 400000 | Not Selected | Program limited by available funding. | R
63 | US212 | Non-NHS | Medium mill and overlay from Tacoma Ave to Carver County Road 36 | 2700000 | Not Selected | Program limited by available funding. | R
60 | US212 | Non-NHS | Medium mill and overlay from Chaska Creek to MN41 | 1700000 | Not Selected | Program limited by available funding. | R
58 | US212 | Non-NHS | Medium mill and overlay from 4 lane section to Chaska Creek | 2700000 | Not Selected | Program limited by available funding. | R
54 | US212 | Non-NHS | Medium mill and overlay from .1 miles south of MN62 to MN62 | 1000000 | Not Selected | Program limited by available funding. | R
76 | US52 | Non-NHS | Medium mill and overlay from Lafayette bridge to I-94 | 200000 | Not Selected | Program limited by available funding. | R
73 | US52 | Non-NHS | Medium mill and overlay from Dakota County Road 42 to Clayton Ave | 800000 | Not Selected | Program limited by available funding. | R
69 | US52 | Non-NHS | Medium mill and overlay from Goodhue/Dakota County Line to County Road 86 | 2300000 | Not Selected | Program limited by available funding. | R
91 | US52 | Non-NHS | Medium mill and overlay from I-494 to Lafayette bridge | 5100000 | Not Selected | Program limited by available funding. | R
72 | US61 | Non-NHS | Medium mill and overlay from US 10 to 70th St | 8500000 | Not Selected | Program limited by available funding. | R
63 | US61 | Non-NHS | Medium mill and overlay from 70th St to Carver Ave | 4400000 | Not Selected | Program limited by available funding. | R
72 | US61 | Non-NHS | Medium mill and overlay from MN96 to White Bear Lake CL | 1000000 | Not selected | RQI does not match on the ground conditions | R
69 | US61 | Non-NHS | Medium mill and overlay from Frenchman Rd to Trailer Pk entrance | 400000 | Not selected | Program limited by available funding. | R
68 | US61 | Non-NHS | Medium mill and overlay from 250th St to Chisago County Road 31/32 | 700000 | Not selected | Program limited by available funding. | R
68 | US61 | Non-NHS | Medium mill and overlay from White Bear Lake Cr to Frenchman Rd | 1800000 | Not selected | Program limited by available funding. | R
67 | US61 | Non-NHS | Medium mill and overlay from Chisago County Road 31/22 to 267th St | 200000 | Not selected | Program limited by available funding. | R
67 | US61 | Non-NHS | Medium mill and overlay from I-94/Mounds Blvd to MN5/7th St | 700000 | Not selected | Program limited by available funding. | R
64 | US61 | Non-NHS | Medium mill and overlay from 170th St to MN97 | 1900000 | Not selected | Program limited by available funding. | R
63 | US61 | Non-NHS | Medium mill and overlay from Trailer Pk entrance to 170th St | 1000000 | Not selected | Program limited by available funding. | R
57 | US61 | Non-NHS | Medium mill and overlay from RP163 to 250TH St | 200000 | Not selected | Program limited by available funding. | R
32 | US61 | Non-NHS | Medium mill and overlay from RP155 to 170th ST | 200000 | Not selected | Program limited by available funding. | R
29 | US61 | Non-NHS | Medium mill and overlay from 267th St to I35 | 300000 | Not selected | Program limited by available funding. | R
65 | US8 | Non-NHS | Medium mill and overlay from Tern Ave roundabout to Minnesota/Wisconsin State line | 1900000 | Not Selected | Program limited by available funding. | R
66 | MN95 | Non-NHS | Medium mill and overlay from St Croxi Trail to Point Rd | 1000000 | Not selected | Program limited by available funding. | R
64 | MN95 | Non-NHS | Medium mill and overlay from Bailey Rd to US61 | 4100000 | Not selected | Program limited by available funding. | R
64 | MN95 | Non-NHS | Medium mill and overlay from Sunrise River to Taylors Falls | 6600000 | Not selected | Program limited by available funding. | R
62 | MN95 | Non-NHS | Medium mill and overlay from I-94 to Valley Creek | 700000 | Not selected | Program limited by available funding. | R
61 | MN95 | Non-NHS | Medium mill and overlay from Valley Creek to Bailey Rd | 1200000 | Not selected | Program limited by available funding. | R
47 | MN95 | Non-NHS | Thin mill and overlay from I-94 to Mulberry St | 18000000 | Not selected | Projected poor pavement conditions. 2020 RSL is 4 to 6 years. | R
44 | MN95 | Non-NHS | Medium mill and overlay from I-94 to .5 miles S of I-94 | 500000 | Not selected | Program limited by available funding. | R
90 | MN95 | Non-NHS | Resurface road from US 8 to MN 36 | 28000000 | 2029 | Projected poor pavement conditions. | Y
87 | MN95 | Non-NHS | Resurface MN 95 from the Isanti county line to the bridge over Sunrise river | 14800000 | 2028 | Poor pavement conditions. 2020 RSL 0 to 5 years. | Y
79 | MN96 | Non-NHS | Resurface road from US 61 to MN 95 | 10280000 | 2030 | Projected poor pavement conditions. | Y
35 | MN97 | Non-NHS | Reconstruct road, trail on Hwy 97 (Scandia Trail N) from 0.24 miles east of I-35/Hwy 61 (Forest Blvd N) and add turn lanes and lighting on Hwy 97 (Scandia Trail N) from west of Everton Ave N to Hwy 61 (Forest Blvd N) in Forest Lake | 10849000 | 2025 | Geometrics. Poor pavement conditions. Ped/bike trail needs. | G
39 | MN97 | Non-NHS | Minor rehabilitation within roundabout at US61 | 100000 | Not selected | Newer concrete roundabouts. | R
81 | MN97 | Non-NHS | Resurface road from US61 to MN95 | 8500000 | 2028 | Poor pavement conditions. Project has been deferred several times. | Y
84 | US10 | Non-NHS | Resurface road from US169/MN47 to Creek Medows Bridge | 15000000 | 2030 | Projected poor pavement conditions. | Y
74 | US10 | Non-NHS | Resurface road from Cleveland/Jarvis to Ramsey Blvd | 11500000 | 2027 | Program limited by available funding. | Y
73 | US10 | Non-NHS | Medium mill and overlay from Cleveland RT/Jarvis LT to Fairoak Ave | 14800000 | 2027 | Poor pavement conditions. | Y
54 | US10 | Non-NHS | Resurface road from MN 65 to the north junction I-35W - Future Project | 7500000 | 2036 | Poor pavement conditions; bad longitudinal joints. | Y
65 | US10 | Non-NHS | Resurface road from US61 to the West end of the St Croix bridge | 2530000 | 2030 | Projected poor pavement conditions. 2020 RSL 10 years. | Y
80 | US12 | Non-NHS | Resurface road from Wright Hennepin county line to County Rd 29 | 8200000 | 2029 | Poor pavement conditions. | Y
85 | US169 | Non-NHS | Repair road from County Rd 15 to Ferry Bridges | 14000000 | 2028 | Poor pavement conditions. | Y
81 | US169 | Non-NHS | Resurface road from 77th Ave N to 101st Ave N | 4400000 | 2029 | Poor pavement conditions. | Y
45 | US169 | Non-NHS | Resurface road from the north end of Bloomington Ferry bridge to Anderson Lakes bridge | 8400000 | 2028 | Poor pavement conditions. | Y
89 | US212 | Non-NHS | Resurface road from County Rd 4 to I-494 | 12700000 | 2028 | Preventive maintenance. | Y
76 | US212 | Non-NHS | Repair and resurface road from Mcleod/Carver County line to MN 5 | 4100000 | 2031 | Preventive maintenance. | Y
67 | US212 | Non-NHS | Repair road from Highway 41 to County Rd. 4 | 18000000 | 2032 | Preventive maintenance. | Y
61 | US212 | Non-NHS | Resurface road from I-494 to MN 62 | 21600000 | 2032 | Poor pavement conditions. | Y
80 | US52 | Non-NHS | Resurface US 52 from Clayton to MN 55 and Resurface MN 55 from County Rd 63 to US 52 | 32500000 | 2028 | Poor pavement conditions. | Y
33 | US61 | Non-NHS | Resurface road from 3rd St. to US 10 | 5000000 | 2032 | Poor pavement conditions. | Y
82 | US61 | Non-NHS | Resurface road from Carver Ave to I94 | 20760000 | 2027 | Poor pavement conditions. | Y
77 | US8 | Non-NHS | Resurface road from W Wyoming Ave to Tern Ave | 24500000 | 2032 | Poor pavement conditions. | Y

## Non-NHS
Score | Route | Description | High Level Cost Estimate for Planning Purposes | Year Planned (FY) | Comments
15 | MN56 | Resurface road from the Goodhue/Dakota County line to MN 50/US 52 | 5180000 | 2031 | Projected poor pavement conditions. 2020 RSL 4 to 11 years.
18 | MN77 | Resurface Hwy 77 (Cedar) from 138th St (CR 23) in Bloomington to the Dakota-Hennepin County line in Apple Valley | 35838000 | 2026, Future | Poor pavement conditions.
19 | MN47 | Resurface road and ADA improvements on Hwy 47 (University Ave) from Cree St to Anoka/Isanti County line in St Francis | 2662000 | 2025 | Safety. Poor pavement conditions.
20 | MN244 | Rebuild road from County Rd. 12 to MN 96 | 4000000 | 2031
21 | MN20 | Resurface road from MN 19 to MN 50 | 5000000 | 2032 | Poor pavement conditions. 2020 RSL 2 to 10 years.
24 | MN5 | Resurface road from County Rd 11 to MN 41 | 5000000 | 2032 | Projected poor pavement conditions.
25 | MN51 | Resurface road from W 7th to Dayton Ave | 6100000 | 2030 | Poor pavement conditions.
27 | MN13 | Medium mill and overlay from Connelly Pkwy to old MN101 | 2000000 | Not selected | Program limited by available funding.
27 | MN13 | Medium mill and overlay from MN13 to MN149 | 200000 | Not selected | Program limited by available funding.
29 | MN65 | Medium mill and overlay from south of E Moore Lake Dr to Anoka County Road 10 | 3100000 | Not Selected | Program limited by available funding.
30 | MN47 | Medium mill and overlay from US10 to .4 miles NW of US10 | 300000 | Not selected | Program limited by available funding.
31 | MN7 | Repair road from W end of 494 bridge. to I-494 | 500000 | 2030 | Poor pavement conditions.
32 | MN47 | Resurface road from 40th Ave to US 10 | 10500000 | 2030 | Poor pavement conditions.
33 | MN47 | Resurface MN 47 from 142nd Ave to 153rd Ave (Alpine Dr) | 1600000 | 2028 | Projected poor pavement conditions. Project has previously been deferred. 2020 RSL 5 years.
33 | MN47 | Resurface road from 153rd Ave (Alpine Dr) to Cree St NW/St. Francis | 15000000 | 2029 | Projected poor pavement conditions.
35 | MN97 | Reconstruct road, trail on Hwy 97 (Scandia Trail N) from 0.24 miles east of I-35/Hwy 61 (Forest Blvd N) and add turn lanes and lighting on Hwy 97 (Scandia Trail N) from west of Everton Ave N to Hwy 61 (Forest Blvd N) in Forest Lake | 10849000 | 2025 | Geometrics. Poor pavement conditions. Ped/bike trail needs.
39 | MN21 | Resurface road from Mill St to US169 | 1500000 | 2031 | Poor pavement conditions.
39 | MN97 | Minor rehabilitation within roundabout at US61 | 100000 | Not selected | Newer concrete roundabouts.
40 | MN13 | Medium mill and overlay from Washburn Ave to I-35 | 1400000 | Not Selected | Program limited by available funding.
43 | MN13 | Reconstruct road from Eagle Creek Ave to County Rd 42 | 3500000 | 2030 | Projected poor pavement conditions.
43 | MN5 | Medium mill and overlay from I-494 to Hennepin/Ramsey County line | 3900000 | Not Selected | Program limited by available funding.
43 | MN65 | Repair road from 217th Ave to Anoka-Isanti County line | 18000000 | 2029 | Repair early distresses.
44 | MN95 | Medium mill and overlay from I-94 to .5 miles S of I-94 | 500000 | Not selected | Program limited by available funding.
46 | MN101 | Repair and resurface road from I-94 to County Rd 38 | 8800000 | 2026 | Poor pavement conditions.
47 | MN19 | Resurface road from the Leseuer/Scott county line to the Scott/Rice county line - Future Project | 2700000 | 2036
47 | MN95 | Thin mill and overlay from I-94 to Mulberry St | 18000000 | Not selected | Projected poor pavement conditions. 2020 RSL is 4 to 6 years.
55 | MN121 | Medium mill and overlay from I35W to Pedestrian bridge | 300000 | Not Selected | Program limited by available funding.
55 | MN5 | Medium mill and overlay from Carver County Road 10 to Oak Ave | 200000 | Not selected | Program limited by available funding.
57 | MN149 | Medium mill and overlay from I-494 to Mendota Heights Rd | 600000 | Not selected | Program limited by available funding.
57 | MN50 | Medium mill and overlay from MN3 to US52 | 4300000 | Not selected | Program limited by available funding.
58 | MN149 | Medium mill and overlay from Mendota Heights Rd to MN5/7th St | 2500000 | Not selected | Program limited by available funding.
59 | MN5 | Medium mill and overlay from MN25 to Carver County Road 10 | 1900000 | Not selected | Program limited by available funding.
60 | MN5 | Repair road from MN 41 to Eden Prairie Rd | 18300000 | 2032 | Much of this is older PCC with ride impacted by isolated crack slabs, some of which are from subsurface utility issues.
60 | MN77 | Medium mill and overlay from Minnesota River bridge to I-494 | 3100000 | Not Selected | Program limited by available funding.
61 | MN101 | Minor concrete pavement repair, from CR 38 to US 10 | 3500000 | 2027 | Poor pavement conditions.
61 | MN47 | Medium mill and overlay from US 10 to Industry Ave | 700000 | Not selected | Program limited by available funding.
61 | MN95 | Medium mill and overlay from Valley Creek to Bailey Rd | 1200000 | Not selected | Program limited by available funding.
62 | MN243 | Medium mill and overlay from MN95 to St Croix River | 700000 | Not selected | Program limited by available funding.
62 | MN95 | Medium mill and overlay from I-94 to Valley Creek | 700000 | Not selected | Program limited by available funding.
64 | MN149 | Medium mill and overlay from Albano Tr to MN55 | 2600000 | Not selected | Program limited by available funding.
64 | MN95 | Medium mill and overlay from Bailey Rd to US61 | 4100000 | Not selected | Program limited by available funding.
64 | MN95 | Medium mill and overlay from Sunrise River to Taylors Falls | 6600000 | Not selected | Program limited by available funding.
65 | MN13 | Medium mill and overlay from Dakota County Line to Washburn Ave | 700000 | Not Selected | Program limited by available funding.
65 | MN5 | Medium mill and overlay from .2 miles W of Carver County Road 10 to .2 miles east of Carver County Road 10 | 200000 | Not selected | Program limited by available funding.
66 | MN13 | Medium mill and overlay from .4 miles west of Dakota Ave to .2 miles east of Dakota ave | 700000 | Not Selected | Program limited by available funding.
66 | MN7 | Medium mill and overlay from I-494 to Shady Oak Road | 1000000 | Not Selected | Program limited by available funding.
66 | MN95 | Medium mill and overlay from St Croxi Trail to Point Rd | 1000000 | Not selected | Program limited by available funding.
67 | MN5 | Resurface road from St. Clair Ave to bridge over I94 | 14439000 | 2028 | Poor pavement conditions.
67 | MN7 | Medium mill and overlay from Railroad bridge to MN100 | 900000 | Not Selected | Program limited by available funding.
68 | MN101 | Medium mill and overlay from NB split with US169 to SB merge with US169 | 3400000 | Not Selected | Program limited by available funding.
68 | MN13 | Medium mill and overlay from MN282 to Scott County Road 21 roundabout | 2000000 | Not selected | Program limited by available funding.
68 | MN65 | Medium mill and overlay from 26th St to 10th ST | 1300000 | Not Selected | Program limited by available funding.
68 | MN95 | Medium mill and overlay from Mulberry to St Saint Croix Trail | 500000 | Not selected | Program limited by available funding.
69 | MN149 | Medium mill and overlay from MN3 to Albano Tr | 200000 | Not selected | Program limited by available funding.
69 | MN3 | Resurface road from 145th St to MN 149 | 4500000 | 2031
69 | MN5 | Medium mill and overlay from Birch St to Scandia Rd | 1100000 | Not selected | Program limited by available funding.
70 | MN101 | Resurface road from Hwy 5 (W 78th St) to Hwy 10/Townline Rd, resurface road, drainage repairs and ADA improvements on Hwy 101 (W 192nd Ave) from Hwy 5 to Townline Rd in Chanhassen/Eden Prairie | 1799000 | 2024 | Poor pavement conditions.
70 | MN13 | Repair concrete from I-494 to MN 55 | 5000000 | 2031
70 | MN51 | Resurface road and ADA improvements on Hwy 51 (Snelling Ave) from Grand Ave to St Clair Ave in St Paul | 1760000 | 2024
70 | MN65 | Resurface road from 37th Ave NE Ave to 53rd NE | 5200000 | 2032 | Projected poor pavement conditions.
71 | MN13 | Medium mill and overlay from Yankee Doodle Rd to I494 | 900000 | Not selected | RQI does not match on the ground conditions
71 | MN3 | Medium mill and overlay from MN149 to Bridge 19045 | 1300000 | Not selected | Program limited by available funding. 2020 Remaining service life 0 to 7 years. Short PCC section driving down Remaining service life.
72 | MN121 | Resurface pavement, signals, drainage and ADA on Hwy 121 (Lyndale Conn) from 0.5 miles west of I-35W pedestrian bridge over Lyndale Ave to W 58th St in Mpls | 1540000 | 2025
72 | MN13 | Medium mill and overlay from Dakota to Washburn ave | 1600000 | Not Selected | Program limited by available funding.
72 | MN3 | Reconstruct the road from Amana Trail to MN 62 | 8800000 | 2031
72 | MN47 | Resurface, drainage, sidewalks and ADA work on Hwy 47 from Hwy 65 to just south of 27th northeast Ave in Mpls | 3400000 | 2027
72 | MN7 | Resurface road from TH 25 to Carver County Line | 6500000 | 2030 | Projected poor pavement conditions.
72 | MN95 | Medium mill and overlay from Point Rd to I-94 | 2800000 | Not selected | RQI does not match on the ground conditions
73 | MN13 | Medium mill and overlay legs to and from Scott County Road 21 roundabout | 300000 | Not selected | Very new pavement either side of new roundabout.
73 | MN21 | Medium mill and overlay from 7th St to Sawmill Rd | 4300000 | Not selected | RQI does not match on the ground conditions
73 | MN3 | Medium mill and overlay from Bridge 19045 to Mendota Rd | 500000 | Not selected | RQI does not match on the ground conditions
73 | MN7 | Medium mill and overlay from Texas Ave to Railroad Bridge | 700000 | Not Selected | RQI does not reflect on the ground conditions
74 | MN13 | Medium mill and overlay from MN13 to Dakota Ave | 700000 | Not Selected | Program limited by available funding.
74 | MN284 | Reconstruct road from US 212 to 122nd St | 11000000 | 2031
74 | MN51 | Medium mill and overlay from Grey Fox Rd to I694 | 300000 | Not selected | Recently repaired in 2021
76 | MN21 | Medium mill and overlay from Sawmill Rd to Mill St | 300000 | Not selected | RQI does not match on the ground conditions
76 | MN50 | Resurface Hwy 50 (240th St) from Hwy 52 (Emery Ave/Rochester Blvd) in Hampton to Hwy 61 in Douglas Township | 6568000 | 2026 | Poor pavement conditions.
77 | MN120 | Resurface road from Ridge Dr to 4th St. | 1200000 | 2031 | Projected poor pavement conditions.
77 | MN21 | Medium mill and overlay from MN19 to Scott County Road 37 | 300000 | Not selected | Program limited by available funding. Short urban section.
77 | MN3 | Resurface road from Rice County line to MN 50 | 6500000 | 2028 | Poor pavement conditions.
78 | MN13 | Medium mill and overlay from Scott County Road 42 to Connelly Pkwy | 700000 | Not selected | RQI does not match on the ground conditions
78 | MN3 | Medium mill and overlay from MN50 to Dakota County Road 58 | 3300000 | Not selected | Program limited by available funding. 2020 Remaining service life is predicted 9 to 15 years.
78 | MN65 | Repair pavement and replace bridges 6817 ( new bridge # 02X06) and 9417 (02X07) over Coon Creek and ADA, signal replacement on Hwy 65 (Central Ave) from CR 10 (Mounds View Blvd) in Spring Lake Park to 217th Ave in East Bethel, cable median barrier from Bunker Lake Blvd to 237th | 39898000 | 2024 | Poor pavement conditions.
78 | MN65 | Resurface road form 53rd Ave NE to South Moore Lake Dr | 3000000 | 2027 | Poor pavement conditions.
78 | MN7 | Medium mill and overlay from Shady Oak Rd to Texas Ave | 3000000 | Not Selected | RQI does not reflect on the ground conditions
79 | MN51 | Resurface, guardrail and ADA on Hwy 51 (Snelling Ave N) from north end of bridge over MN 36 in Roseville to 0.1 mile north of Grey Fox Rd in Arden Hills | 6477000 | 2026 | Poor pavement conditions. ADA, bike/ped, and drainage needs.
79 | MN96 | Resurface road from US 61 to MN 95 | 10280000 | 2030 | Projected poor pavement conditions.
81 | MN5 | Medium mill and overlay from Hennepin/Ramsey County Line to Munster Ave | 600000 | Not selected | Not selected. Program limited by available funding. Short section of PCC before and after river bridge. Bridge surface is pulling average RQI down.
81 | MN7 | Resurface road from the Hennepin/Carver County line to Division St | 23100000 | 2031 | Recent resurfacing project. Construction in progress at time of DIV run. Roughness at intersection contribute to poor ride.
81 | MN97 | Resurface road from US61 to MN95 | 8500000 | 2028 | Poor pavement conditions. Project has been deferred several times.
87 | MN120 | Reconstruct road from 4th St in Maplewood to Hwy 244 in White Bear Lake | 15559000 | 2027
87 | MN95 | Resurface MN 95 from the Isanti county line to the bridge over Sunrise river | 14800000 | 2028 | Poor pavement conditions. 2020 RSL 0 to 5 years.
90 | MN13 | Medium mill and overlay from I-35W to Yankee Doodle Rd | 6900000 | Not selected | RQI does not match on the ground conditions
90 | MN95 | Resurface road from US 8 to MN 36 | 28000000 | 2029 | Projected poor pavement conditions.