## Definitions
This is a list of the columns in the checklist and what the column contents are supposed to be.
Project SB # | In this cell put the project specific SB number
Special Provision Title | This cell contains the specific title of the special provision
Description | This cell contains a description of the submittal that is required
Lead Time Prior to Activity | This cell contains the required days (calendar or working) a submittal has to be submitted before an activity can commence
MnDOT Req'd Form (Y/N) | This cells is a yes or no cell that shows if there is a form for the submittal housed on MnDOT's website
Subcontractor name | In this cell put the name of the subcontractor responsible for completing the work.
Rev. # | This cell is the revision number given to the submittal
Submittal received date | This cell is the date that the project engineer received the submittal from the contractor
Reviewed by | This cells shows the project engineer where to send the submittal to
Date sent to Reviewer | This cell is the date that the project engineer sends the submittal to the reviewer
Date due | This is the date that the reviewer should be done with reviewing the submittal
Date received | This is the date that the project engineer receives the submittal from the reviewer
Days (Due - Received) | This cell is a formula that calculates the days between the due date and received date. Positive numbers mean it is on schedule and negative numbers means its over due
Submittal Status | This cell contains a drop down list of different responses from MnDOT
Date response sent to contractor | This is the date that the project engineer sent the submittal back to the contractor

## Read Me
Instructions
Step 1 worksheet
1 | Populate SB # column
2 | Indicate if the SB is included in the contract by marking it with an "x" in Column F
3 | Click "Create Table" button. This will populate the start of the "Final Checklist" tab.
Step 2 Tab - Specialty SB's worksheet
4 | Populate project specific SB's in the table provided. These will have to be read by the project engiener to identify submittals. Enter the submittals and reference sections in this worksheet.
5 | After completing specialty SB's in the worksheet, highlight the range data in columns A through P and down to the last entry. Cut and Paste values to the first available row at the end of the "Final Checklist" worksheet.
6 | The user can use the filters at the top of the page to sort the available data by SB # or provide other sorting. For instance, Cell A4 would be sorted from smallest to largest to get the SB-numbers in order. The Final Checklist worksheet will be a printable record for using at weekly meetings if desired.

## Step 1
** Instructions 1 - Populate SB # Column ; 2 - Indicate if the SP is included in the contract by marking it with an "x" in column F 3 - Click "Create Table" 4 -In the "Step 2 - Specialty SB's" tab, populate project specific in the table provided 5 - Copy and paste Specialty SB's table manually created at the bottom of the Final Checklist populated by the macro in Step 3
SB # | Special Provision | Included in Contract? | Macros must be enabled for table to be created correctly
1 | Self Consolidating Concrete | x
High Performance Concrete Bridge Decks
Mass Concrete
2 | Special Surface Finish of Concrete Surfaces | x
Split Median Barrier Cap
Connections
Expansion Joint Devices
Modular Bridge Joint System
Fabrication Requirements
Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating)
Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
High-Load Multi-Rotational Bearings
Threaded Rod Anchorages
Ultrasonic Impact Treatment
Texture Planing of Bridge Wearing Course
Beam Camber and Deflection
Prestressed Concrete Beam End Zone Crack Repair
Post Tensioning System
Crack Pretreatment for Chip Seal Wearing Course
Polymer Wearing Course Type Epoxy
Polymer Wearing Course Type Epoxy - Urethane
Remove and Patch Monolithic Slab
Methyl Methacrylate (MMA) Flood Seal
22 | Repair Structural Cracks (Epoxy Injection) | x
Replace Waterproof Gland in Expansion Joint Device
16 | Type St Anchorages | x
15 | Reinforcement Bar Anchorages (Post-installed) | x
Temporary Portable Precast Concrete Barrier Anchorage Installation and Removal
Repair Paving Bracket
Bearing Keeper
Clean and Grease Expansion Bearing Assemblies
Concrete Surface Repair
Paint Concrete (Metalizing)
Drilled Shaft Construction
Structural Metals
CRSI Certification
Paint Removal and Waste Disposal of Non-Lead/PCB Paint
Paint Removal and Waste Disposal of Lead/PCB Paint
Powder Coating System
Organic Zinc-Rich Paint System
Protection of Non-Painted Surfaces
Clean and Prime Top Flange
Inorganic Zinc-Rich Paint System
Protection of Non-Painted Surfaces
Employee Health and Welfare
Progress Schedules
Distributed Galvanic Anode
Create Table
If there is an error and Excel is not updating or running properly, try clicking this button first.

## Step 2 - Specialty SB's
State Project: (#)(followed by description) | [6 empty] | (Contractor's Name) | [9 empty] | **Instructions - Populate Table, then copy and paste values into Final Checklist tab after last entry in table
Example data shown in yellow at time of opening spreadsheet. Delete and place own data.
[6 empty] | Contractor |  | Project Engineer
SB # | Special Provision Title | SUB-SECT. | Description | Lead Time Prior to Activity | MnDOT Req'd Form (Y/N) | Subcontractor name | Rev. # | Submittal received date | Reviewed by | Date sent to Reviewer | Date due | Date received | Days (Due - Received) | Submittal Status | Date response sent to contractor | Designers Note?
8 | Paint Bearing Assembly | X.X | Water Treatment Plan | [5 empty] | Project Engineer |  |  |  | 0
9 | CFRP/GFRP Concrete Patch | X.X | Materials | 12 weeks before start of work |  |  |  |  | Project Engineer |  |  |  | 0
8.1 | CFRP/GFRP Concrete Patch | X.X | FRP and adhesive comp.s, product data | 12 weeks before start of work |  |  |  |  | Project Engineer |  |  |  | 0
13 | CFRP/GFRP Concrete Patch | X.X | CFRP designs w/ manufacturer properties | 12 weeks before start of work |  |  |  |  | Project Engineer |  |  |  | 0
13.1 | CFRP/GFRP Concrete Patch | X.X | Manufacturer recommended repair procedures | 12 weeks before start of work |  |  |  |  | Project Engineer |  |  |  | 0
13.2 | CFRP/GFRP Concrete Patch | X.X | FRP layer details & adhesive composite system | 12 weeks before start of work |  |  |  |  | Project Engineer |  |  |  | 0
13.3 | CFRP/GFRP Concrete Patch | X.X | Detail drawings, coating system, construction device details, list of QC personnel, Manufacturer's field rep | 12 weeks before start of work |  |  |  |  | Project Engineer |  |  |  | 0
13.4 | CFRP/GFRP Concrete Patch | X.X | Corrective Work | 2 weeks before beginning corrective work |  |  |  |  | Project Engineer |  |  |  | 0
17 | Temporary Structural Beam Support | X.X | Geotechnical investigation and analysis, temp support calcs and plans, work plan - shoring type, method of removals w/ shoring in place, engineering calcs for shoring type, shoring design | [5 empty] | Project Engineer |  |  |  | 0

## Final Checklist
SP 2789-151 | [6 empty] | (Contractor's Name)
[6 empty] | Contractor |  | Project Engineer
SB # | Special Provision Title | SUB-SECT. | Description | Lead Time Prior to Activity | MnDOT Req'd Form (Y/N) | Subcontractor name | Rev. # | Submittal received date | Reviewed by | Date sent to Reviewer | Date due | Date received | Days (Due - Received) | Submittal Status | Date response sent to contractor | Designers Note?
1 | Self Consolidating Concrete | 2.A.6 | Concrete Mix Design | 21 Cal. Days before placement | Y |  |  |  | Concrete Office |  |  |  | 0
1 | Self Consolidating Concrete | 2.A.6.b | Laboratory Mixing | 14 Cal. Days before prelim. lab mixing | Y |  |  |  | Concrete Office |  |  |  | 0
1 | Self Consolidating Concrete | 2.A.7.b | JMF Adjustment | After Lab Mix if agg. not approved | N |  |  |  | Concrete Office |  |  |  | 0
1 | Self Consolidating Concrete | 2.A.8 | Laboratory Test Data | 15 Work Days before trial placement | N |  |  |  | Concrete Office |  |  |  | 0
2 | Special Surface Finish of Concrete Surfaces | 4 | Falsework Plans | 6 weeks before starting construction | N |  |  |  | RBCE |  |  |  | 0 |  |  | X
2 | Special Surface Finish of Concrete Surfaces | 2.B | Materials |  | N |  |  |  | Concrete Office |  |  |  | 0
2 | Special Surface Finish of Concrete Surfaces | 3.B | Materials |  | N |  |  |  | Concrete Office |  |  |  | 0
2 | Special Surface Finish of Concrete Surfaces | 3.C | Quality Control Plan, Contractor qualifications and documentation | 20 days prior to executing work | N |  |  |  | RBCE |  |  |  | 0
2 | Special Surface Finish of Concrete Surfaces | 3.b(1) | Detailed Plans for Placing Concrete | 2 weeks before casing Bridge Slab Concrete | N |  |  |  | RBCE |  |  |  | 0
2 | Special Surface Finish of Concrete Surfaces | 2.B | SSF II Sample |  | N |  |  |  | RBCE |  |  |  | 0
2 | Special Surface Finish of Concrete Surfaces | 2.C | Quality Control Plan, Contractor qualifications and documentation | 20 days prior to executing work | N |  |  |  | RBCE |  |  |  | 0
2 | Special Surface Finish of Concrete Surfaces | 2.C | Contractor Qualifications and Documentation | 5 Working days before each SSF II Application | N |  |  |  | RBCE |  |  |  | 0
22 | Repair Structural Cracks (Epoxy Injection) | B.1 | 3 copies of material certification |  | N |  |  |  | Project Engineer |  |  |  | 0
22 | Repair Structural Cracks (Epoxy Injection) | B.2 | Safety Data Sheets |  | N |  |  |  | Project Engineer |  |  |  | 0
22 | Repair Structural Cracks (Epoxy Injection) | B.3 | Manufacturer's published recs for product used |  | N |  |  |  | Project Engineer |  |  |  | 0
22 | Repair Structural Cracks (Epoxy Injection) | B.4 | Type and installation procedure for injection ports |  | N |  |  |  | Project Engineer |  |  |  | 0
16 | Type St Anchorages | A | ACI Certification, MPII Copy, Adhesive meets req'ts |  | Y |  |  |  | Project Engineer |  |  |  | 0
16 | Type St Anchorages | B | Production Anchorages Qualification Test Report |  | Included w/ Production Anchorages Qualification Test Report |  |  |  | Project Engineer |  |  |  | 0
15 | Reinforcement Bar Anchorages (Post-installed) | C | Anchorage Replacement Plan |  | N |  |  |  | Project Engineer |  |  |  | 0
15 | Reinforcement Bar Anchorages (Post-installed) | C | Production Anchorages Qualification Test Report |  | Y |  |  |  | Project Engineer |  |  |  | 0
15 | Reinforcement Bar Anchorages (Post-installed) | B | ACI-CRSI Certification |  | Y |  |  |  | Project Engineer |  |  |  | 0

## Boiler Plate SB's
State Project: (#)(followed by description) | [6 empty] | (Contractor's Name)
[6 empty] | Contractor |  | Project Engineer | [8 empty] | Bridge Office Use Only
SB # | Special Provision Title | SUB-SECT. | Description | Lead Time Prior to Activity | MnDOT Req'd Form (Y/N) | Subcontractor name | Rev. # | Submital received date | Reviewed by | Date sent to Reviewer | Date due | Date received | Days (Due - Received) | Submital Status | Date response sent to contractor | Designers Note? | SB2018-# | SB SUBSECTION | Title | Included in SP?
| Restrictions on movement and storage of heavy loads and equipment | 0 | Proposed loads and structural analysis of deck and beams certifed by a PE | 7 Cal days before placement of loads | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 1513 |  | Restrictions on movement and storage of heavy loads and equipment
| Employee Health and Welfare |  | Safety Plan |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 1706 |  | Employee Health and Welfare
| Construction Operations Adjacent to roadways |  | 5 copies of detailed plans/specs and 2 copies of calcs of proposed system | 6 weeks before starting construction | N |  |  |  | Project Engineer | [6 empty] | X | 1707 |  | Construction Operations Adjacent to roadways
| Navigable Waterways | 0 | Plans showing location & dimensions of cofferdams & other temp. constr. which may affect navigation, & method of furnishing, installing, operating and maintaining navigation lights |  | N |  |  |  | Coast Guard |  |  |  | 0 |  |  | X | 1709 |  | Navigable Waterways
| Progress Schedules |  | Schedule for scheme and sequence of operations |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 1803 |  | Progress Schedules
| Connections | G.2.c(5) | Quality Control Plan | 4 weeks before start of steel erection | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2402.1 | G.2.c(5) | Connections
| Expansion Joint Devices | A.1 | Joint Seal Material |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.4 | A.1 | Expansion Joint Devices
| Expansion Joint Devices | B.1 | Quality Manual, Non-Conformance report | 30 Cal. Days before beginning work | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.4 | B.1 | Expansion Joint Devices
| Modular Bridge Joint System | B | Modular Bridge Joint System test results | Prior to Manufacture | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.5 | B | Modular Bridge Joint System
| Modular Bridge Joint System | D.8 | Modular Bridge Joint System test results |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.5 | D.8 | Modular Bridge Joint System
| Modular Bridge Joint System | E.4 | Maintenance and Parts replacement plan |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.5 | E.4 | Modular Bridge Joint System
| Modular Bridge Joint System | F.1 | Submittals |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.5 | F.1 | Modular Bridge Joint System
| Modular Bridge Joint System | F.2 | Submittals | [5 empty] | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.5 | F.2 | Modular Bridge Joint System
| Modular Bridge Joint System | F.3 | Submittals | [5 empty] | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.5 | F.3 | Modular Bridge Joint System
| Fabrication Requirements | G | Quality Manual | 30 Cal Days before beginning work | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.5 | G | Fabrication Requirements
| Fabrication Requirements | G | Non-Conformance report |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.5 | G | Fabrication Requirements
| High-Load Multi-Rotational Bearings | B | Quality Manual | 30 Cal. Days before beginning work | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.7 | B | High-Load Multi-Rotational Bearings
| High-Load Multi-Rotational Bearings | C | Pot Bearing Test | 30 Cal. Days before starting of test operations | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.7 | C | High-Load Multi-Rotational Bearings
| High-Load Multi-Rotational Bearings | D | Disc Bearing Test | 30 Cal. Days before starting of test operations | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.7 | D | High-Load Multi-Rotational Bearings
| Threaded Rod Anchorages | A | ACI Certification, MPII, Verification adhesive has uncracked characteristic bond, Adhesive |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2402.8 | A | Threaded Rod Anchorages
| Threaded Rod Anchorages | B | Non-conformance report |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2402.8 | B | Threaded Rod Anchorages
| Texture Planing of Bridge Wearing Course |  | Notification of plans to perform texture planing | 24 hrs before beginning texture planing |  |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2404.3 |  | Texture Planing of Bridge Wearing Course
| Post Tensioning System | B.1 | Prestressed concrete working drawings, Post Tensioning Calculations, Prestressed tendons grouting details |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2405.1 | B.1 | Post Tensioning System |  | Repeats (Specific Gravity and Absportion Data)
| Post Tensioning System | B.3 | Post Tensioning shop drawings |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2405.1 | B.3 | Post Tensioning System
| Post Tensioning System | D.3 | Theoretical elongation revisions |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2405.1 | D.3 | Post Tensioning System |  | Repeats (Specific Gravity and Absportion Data)
| Post Tensioning System | D.3.b | Load extension test data, Calibration Chart, Initial Calibration Data |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2405.1 | D.3.b | Post Tensioning System
| Post Tensioning System | D.4.c | Gauage Pressures and elongations |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2405.1 | D.4.c | Post Tensioning System
| Post Tensioning System | D.5.a | Grouting operations plan |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2405.1 | D.5.a | Post Tensioning System
| Beam Camber and Deflection | J.1 | Record of Camber, Beam and residual camber calculations |  | Y |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2405.2 | J.1 | Beam Camber and Deflection
| Prestressed Concrete Beam End Zone Crack Repair | 2.c | Epoxy Materials and injection procedure | 7 Cal Days before proceeding with epoxy injection | N |  |  |  | Materials Engineer |  |  |  | 0 |  |  |  | 2405.6 | 2.c | Prestressed Concrete Beam End Zone Crack Repair
| Crack Pretreatment for Chip Seal Wearing Course | B.3 | Epoxy wearing course Data sheets | 20 Work days befoe applying Epoxy | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2407.1 | B.3 | Crack Pretreatment for Chip Seal Wearing Course
| Polymer Wearing Course Type Epoxy | B.5 | Polymer Wearing course data sheets, certified test report |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2407.2 | B.5 | Polymer Wearing Course Type Epoxy
| Polymer Wearing Course Type Epoxy | C.2.a | Dust abatement plan | 14 days before start of work | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2407.2 | C.2.a | Polymer Wearing Course Type Epoxy
| Polymer Wearing Course Type Epoxy | C.3.f | Alternative deck patch material |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2407.2 | C.3.f | Polymer Wearing Course Type Epoxy
| Polymer Wearing Course Type Epoxy | C.7 | Polymer wearing course repair procedures |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2407.2 | C.7 | Polymer Wearing Course Type Epoxy
| Polymer Wearing Course Type Epoxy - Urethane | B.5 | Data Sheets and Specs, test reports | 20 Work days before application | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2407.3 | B.5 | Polymer Wearing Course Type Epoxy - Urethane
| Polymer Wearing Course Type Epoxy - Urethane | C.1 | Recommended procedures, Certification for waiving of manufacturer representative |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2407.3 | C.1 | Polymer Wearing Course Type Epoxy - Urethane
| Polymer Wearing Course Type Epoxy - Urethane | C.7 | Repair Procedures |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2407.3 | C.7 | Polymer Wearing Course Type Epoxy - Urethane
| Concrete Surface Repair | XX | Qualification of shotcrete Crew |  | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | Proposed method of application, mix design, curing procedure & protection |  | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | QC testing program |  | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | Name of preblended, packaged product |  | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | If over traffic/pedestrians, proposed mechanical anchors to help bond strength |  | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | Supplier name and mix i.d. | Where Contractor-designed dry shotcrete mix is provided | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | In-situ testing results | Where Contractor-designed dry shotcrete mix is provided | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | Materials & proportions on a lb/cf basis, chlorine ion content & test method | Where Contractor-designed dry shotcrete mix is provided | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | Documentation of compatibility of admixtures and concrete mix | Where Contractor-designed dry shotcrete mix is provided | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Concrete Surface Repair | XX | Manufacturer QC program | Where Contractor-designed dry shotcrete mix is provided | N | [7 empty] | 0 |  |  |  | 2433.13 | XX | Concrete Surface Repair |  |  | X
| Paint Removal and Waste Disposal of Lead/PCB Paint | C | Exposure Plan, Containment Details, Disposal of Waste Materials |  | N |  |  |  | Project Engineer, Owners/ Occupants of Nearby Buildings |  |  |  | 0 |  |  |  | 2476.2 | C | Paint Removal and Waste Disposal of Lead/PCB Paint
| Powder Coating System | A | Quality Manual | 30 Cal. Days before work | Y |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | A | Powder Coating System
| Powder Coating System | A | Non-conformance report |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | A | Powder Coating System
| Powder Coating System | C.1 | Quality Manual | As work is being performed | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | C.1 | Powder Coating System
| Powder Coating System | D.1.b(1) | Non-conformance report |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | D.1.b(1) | Powder Coating System
| Powder Coating System | E.1 | Powder manufacturer's trained personnel, Coating repair procedures |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | E.1 | Powder Coating System
| Powder Coating System | H.1 | Non-Conformance repair plan |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | H.1 | Powder Coating System
| Powder Coating System | H.2 | Non-Conformance repair plan |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | H.2 | Powder Coating System
| Powder Coating System | A | Quality Manual | 30 Cal. Days before work | Y |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | A | Powder Coating System
| Powder Coating System | A | Non-conformance report |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | A | Powder Coating System
| Powder Coating System | C.1 | Quality Manual | As work is being performed | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | C.1 | Powder Coating System
| Powder Coating System | D.1.b(1) | Non-conformance report |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | D.1.b(1) | Powder Coating System
| Powder Coating System | E.1 | Powder manufacturer's trained personnel |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | E.1 | Powder Coating System
| Powder Coating System | E.1 | Coating repair procedures |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | E.1 | Powder Coating System
| Powder Coating System | H.1 | Non-Conformance repair plan |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | H.1 | Powder Coating System
| Powder Coating System | H.2 | Non-Conformance repair plan |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2477.3 | H.2 | Powder Coating System
| Organic Zinc-Rich Paint System |  | Coating Inspection Requirements Records | At completion of job | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2478 |  | Organic Zinc-Rich Paint System
| Organic Zinc-Rich Paint System |  | Non-Conformance repair plan |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  | X | 2478.1 |  | Organic Zinc-Rich Paint System
| Protection of Non-Painted Surfaces |  | Non-Conformance repair plan |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2478.1 |  | Protection of Non-Painted Surfaces
| Organic Zinc-Rich Paint System | B | Plan for removal and collection of non-tightly adhered paint residue |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2478.3 | B | Organic Zinc-Rich Paint System
| Clean and Prime Top Flange | B | Remove and collect non-tightly adhered paint residue plan |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2478.3 | B | Clean and Prime Top Flange
| Inorganic Zinc-Rich Paint System |  | Coating Inspection Requirements Records |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2479 |  | Inorganic Zinc-Rich Paint System
| Protection of Non-Painted Surfaces |  | Non-conformance report |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2479.1 |  | Protection of Non-Painted Surfaces
| Protection of Non-Painted Surfaces |  | Non-conformance report |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2479.1 |  | Protection of Non-Painted Surfaces
| Conduit Systems | 0 | 3 Sets of erection drawings of each conduit system |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2545 |  | Conduit Systems
| Fencing | C.1 | List of fence components, suppliers, and fabricators |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2557 | C.1 | Fencing
| Fasteners | 0 | Documentation meeting ASTM F3125 and fastener assemblies |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 3391 |  | Fasteners
| Galvanized Structural Shapes | 0 | Non-Conformance Report for each repair of galvanized surface |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 3394 |  | Galvanized Structural Shapes
| Self Consolidating Concrete | 2.A.6 | Concrete Mix Design | 21 Cal. Days before placement | Y |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 A | 2.A.6 | Self Consolidating Concrete
| Self Consolidating Concrete | 2.A.6.b | Laboratory Mixing | 14 Cal. Days before prelim. lab mixing | Y |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 A | 2.A.6.b | Self Consolidating Concrete
| Self Consolidating Concrete | 2.A.7.b | JMF Adjustment | After Lab Mix if agg. not approved | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 A | 2.A.7.b | Self Consolidating Concrete
| Self Consolidating Concrete | 2.A.8 | Laboratory Test Data | 15 Work Days before trial placement | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 A | 2.A.8 | Self Consolidating Concrete
| High Performance Concrete Bridge Decks | 2.A.5.b(1) | Fibers | Only if using single component fibers? | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.5.b(1) | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.5.b(4) | Alternative methods for adding fibers |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.5.b(4) | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.6 | Concrete Mix Design | 21 Cal. Days before placement | Y |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.6 | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.6 | Laboratory Mixing Data |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.6 | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.6.b | Laboratory Mixing | 14 Cal. Days before prelim. lab mixing | Y |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.6.b | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.6.b | Laboratory Mixing Data |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.6.b | High Performance Concrete Bridge Decks |  |  | Designers Note
| High Performance Concrete Bridge Decks | 2.A.7.b | JMF Adjustment |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.7.b | High Performance Concrete Bridge Decks |  |  | Designers Note
| High Performance Concrete Bridge Decks | 2.A.8 | Laboratory Test Data | 15 Work Days before trial placement | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.8 | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.9.a | Waive Trial Placement for Bridge Deck Slab | 14 Cal. Days before placing bridge deck slab concrete | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.9.a | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.9.b | Slab Placement and Curing Plan | 14 Cal. Days before placing bridge deck slab concrete | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.9.b | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.9.c | National Weather Service Forecast | 3 hrs before slab placement | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 B | 2.A.9.c | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.3.C.4 | Fine Grade Sand Material Data |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 B | 2.3.C.4 | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.7.b | JMF Adjustment Concrete Mix Design | After Lab Mix if agg. not approved | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 C | 2.A.7.b | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.6 | Concrete Mix Design | 21 Cal. Days before placement | Y |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 C | 2.A.6 | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.6.b | Laboratory Mixing | 14 Cal. Days before prelim. lab mixing | Y |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 C | 2.A.6.b | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.8 | Laboratory Test Data | 15 Work Days before trial placement | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 C | 2.A.8 | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.9.a | Waive Trial Placement for Bridge Deck Slab |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 C | 2.A.9.a | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.9.b | Slab Placement and Curing Plan | 14 Cal. Days before slab placement | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 C | 2.A.9.b | High Performance Concrete Bridge Decks
| High Performance Concrete Bridge Decks | 2.A.9.c | National Weather Service Forecast | 3 hrs before slab placement | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 C | 2.A.9.c | High Performance Concrete Bridge Decks
| Mass Concrete | 2.A.6 | Laboratory Mixing Data |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 D | 2.A.6 | Mass Concrete
| Mass Concrete | 3.B.1.6 | Heat of Hydration by use of Cooling Tubes |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 D | 3.B.1.6 | Mass Concrete
| Mass Concrete | 2.A.6 | Concrete Mix Design | 21 Cal. Days before placement | Y |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 D | 2.A.6 | Mass Concrete
| Mass Concrete | 2.A.6.b | Laboratory Mixing | 14 Cal. Days before prelim lab mixing and testing | Y |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 D | 2.A.6.b | Mass Concrete
| Mass Concrete | 2.A.6.b | Laboratory Mixing Data |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 D | 2.A.6.b | Mass Concrete
| Mass Concrete | 2.A.7.b | JMF Adjustment Concrete Mix Design | After Lab Mix if agg. not approved | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 D | 2.A.7.b | Mass Concrete
| Mass Concrete | 2.A.8 | Laboratory Test Data of Concrete Mix Design | 15 Work Days before trial placement | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 D | 2.A.8 | Mass Concrete
| Mass Concrete | 3.A.1 | Placement and Temperature Plan | 60 Cal. Days | Y |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 D | 3.A.1 | Mass Concrete
| Mass Concrete | 3.B.1 | Placement and Temperature Plan | 30 Cal. Days before casting mass concrete | Y |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.2 D | 3.B.1 | Mass Concrete
| Mass Concrete | 3.B.2 (f) | Temperature Monitoring |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.2 D | 3.B.2 (f) | Mass Concrete
| Special Surface Finish of Concrete Surfaces | 4 | Falsework Plans | 6 weeks before starting construction | N |  |  |  | RBCE |  |  |  | 0 |  |  | X | 2401.3 B | 4 | Special Surface Finish of Concrete Surfaces
| Special Surface Finish of Concrete Surfaces | 2.B | Materials |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.3 F | 2.B | Special Surface Finish of Concrete Surfaces
| Special Surface Finish of Concrete Surfaces | 3.B | Materials |  | N |  |  |  | Concrete Office |  |  |  | 0 |  |  |  | 2401.3 F | 3.B | Special Surface Finish of Concrete Surfaces
| Special Surface Finish of Concrete Surfaces | 3.C | Quality Control Plan, Contractor qualifications and documentation | 20 days prior to executing work | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.3 F | 3.C | Special Surface Finish of Concrete Surfaces
| Special Surface Finish of Concrete Surfaces | 3.b(1) | Detailed Plans for Placing Concrete | 2 weeks before casing Bridge Slab Concrete | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.3 F | 3.b(1) | Special Surface Finish of Concrete Surfaces
| Special Surface Finish of Concrete Surfaces | 2.B | SSF II Sample |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.3 F | 2.B | Special Surface Finish of Concrete Surfaces
| Special Surface Finish of Concrete Surfaces | 2.C | Quality Control Plan, Contractor qualifications and documentation | 20 days prior to executing work | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.3 F | 2.C | Special Surface Finish of Concrete Surfaces
| Special Surface Finish of Concrete Surfaces | 2.C | Contractor Qualifications and Documentation | 5 Working days before each SSF II Application | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.3 F 2 | 2.C | Special Surface Finish of Concrete Surfaces
| Split Median Barrier Cap | B.2 | Alternative Materials |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2401.3 I | B.2 | Split Median Barrier Cap
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating) | D | Welding Procedure Specifications |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 PC | D | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating) | D | Quality Manual | 5 Working days prior to beginning work | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 PC | D | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating) | E.6 | Galvanizing Requirements |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 PC | E.6 | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating) | E.8 | Galvanizing Requirements | 5 Working days before intending to galvanize | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 PC | E.8 | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating) | G | QC/QA, Anchorage Tolerances |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 PC | G | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Powder Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating) | D | QC/QA, Welding Procedure Specifications |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 WP | D | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating) | D | Quality Manual | 5 Working days before beginning work | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 WP | D | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating) | E.6 | Quality Control |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 WP | E.6 | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating) | E.8 | QA Audit | 5 Working days before intending to galvanize | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 WP | E.8 | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating) | F | Intent to Ship | 5 Working days before intent to ship | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 WP | F | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating) | G | QC/QA, CIP Anchorage Placement in Forms |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6 WP | G | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating) | H.1 | Non-Conformance repair plan |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6WP | H.1 | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
| Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating) | H.2 | Non-Conformance repair plan |  | N |  |  |  | Structural Metals Engineer |  |  |  | 0 |  |  |  | 2402.6WP | H.2 | Metal Railing ("Duplex Coated" using Hot-dipped Galvanizing and Paint Coating)
| Ultrasonic Impact Treatment | A | Preliminary Work and Mobilization Task |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2402.9A | A | Ultrasonic Impact Treatment
| Ultrasonic Impact Treatment | C | Letter of Retrofit work |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2402.9A | C | Ultrasonic Impact Treatment
| Bearing Keeper | D | QC/QA |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.11 A | D | Bearing Keeper
| Clean and Grease Expansion Bearing Assemblies | B.1 | Jacking scheme |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2433.11 B | B.1 | Clean and Grease Expansion Bearing Assemblies
| Distributed Galvanic Anode | X.X | Shop Drawings | 6 weeks before installation | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.14 D | X.X | Distributed Galvanic Anode
| Remove and Patch Monolithic Slab | Mono | Early strength concrete mix results - Type A,B,C, D, E,F |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  | X | 2433.3 Mono | Mono | Remove and Patch Monolithic Slab
| Remove and Patch Structural Slab | WC | Early strength concrete mix results - Type A,B,C, D, E,F |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  | X | 2433.3 WC | WC | Remove and Patch Structural Slab
| Repair Structural Cracks (Epoxy Injection) | B.1 | 3 copies of material certification |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.5 B | B.1 | Repair Structural Cracks (Epoxy Injection)
| Repair Structural Cracks (Epoxy Injection) | B.2 | Safety Data Sheets |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.5 B | B.2 | Repair Structural Cracks (Epoxy Injection)
| Repair Structural Cracks (Epoxy Injection) | B.3 | Manufacturer's published recs for product used |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.5 B | B.3 | Repair Structural Cracks (Epoxy Injection)
| Repair Structural Cracks (Epoxy Injection) | B.4 | Type and installation procedure for injection ports |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.5 B | B.4 | Repair Structural Cracks (Epoxy Injection)
| Methyl Methacrylate (MMA) Flood Seal | C.3 | Sand material data, storage, and use plan |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2433.5 Flood | C.3 | Methyl Methacrylate (MMA) Flood Seal
| Methyl Methacrylate (MMA) Flood Seal | E | Evidence /References for Waiving of tech rep from manufacturer |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2433.5 Flood | E | Methyl Methacrylate (MMA) Flood Seal
| Methyl Methacrylate (MMA) Flood Seal | B.3 | MMA Manufacturers Instructions |  | N |  |  |  | RBCE |  |  |  | 0 |  |  |  | 2433.5 Flood C.3 | B.3 | Methyl Methacrylate (MMA) Flood Seal
| Replace Waterproof Gland in Expansion Joint Device | A.3 | Seal material testing |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2433.7 A | A.3 | Replace Waterproof Gland in Expansion Joint Device
| Replace Waterproof Gland in Expansion Joint Device | A.4 | Test Results |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2433.7 A | A.4 | Replace Waterproof Gland in Expansion Joint Device
| Replace Waterproof Gland in Expansion Joint Device | B | Information for lubricants not on MnDOT's Approved/ Qualified List |  | N |  |  |  | Fabrication Methods Engineer |  |  |  | 0 |  |  |  | 2433.7 A | B | Replace Waterproof Gland in Expansion Joint Device
| Type St Anchorages | A | ACI Certification, MPII Copy, Adhesive meets req'mts |  | Y |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.8 A | A | Type St Anchorages
| Type St Anchorages | B | Production Anchorages Qualification Test Report |  | Included w/ Production Anchorages Qualification Test Report |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.8 A | B | Type St Anchorages
| Reinforcement Bar Anchorages (Post-installed) | C | Anchorage Replacment Plan |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.8 C | C | Reinforcement Bar Anchorages (Post-installed)
| Reinforcement Bar Anchorages (Post-installed) | C | Production Anchorages Qualification Test Report |  | Y |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.8 C | C | Reinforcement Bar Anchorages (Post-installed)
| Reinforcement Bar Anchorages (Post-installed) | B | ACI-CRSI Certification |  | Y |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.8 C | B | Reinforcement Bar Anchorages (Post-installed)
| Temporary Portable Precast Concrete Barrier Anchorage Installation and Removal | A | ACI-CRSI Certification, MPII, Verification adhesive has uncracked characteristic bond |  | Y |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.8 D | A | Temporary Portable Precast Concrete Barrier Anchorage Installation and Removal
| Temporary Portable Precast Concrete Barrier Anchorage Installation and Removal | B | Non Comforance Anchorage Replacement Plan |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.8 D | B | Temporary Portable Precast Concrete Barrier Anchorage Installation and Removal
| Repair Paving Bracket | C | Repair Paving Bracket test data, Manufacturer Job Specific Req'mts |  | N |  |  |  | Project Engineer |  |  |  | 0 |  |  |  | 2433.9 A | C | Repair Paving Bracket